# Midland Cancer Network Executive Group

# Progress Report – July - September 2009

# Introduction

This report covers the Midland Cancer Network (MCN) quarter one 1 July 2009 – 30 September 2009.  This report summarises progress to date on the MCN work programme. This report summarises progress related to:

- network governance and fostering clinical leadership

- lung cancer

- bowel cancer

- palliative care

- non-surgical cancer treatment service planning

- reducing inequalities

- other MCN work programme activities.

# Network Governance and Clinical Leadership

- Sue Hayward, Director of Nursing Waikato DHB has agreed to represent the Midland Directors of Nursing on the Executive Group and chair the Midland Care Coordinators forum.

- The Midland Colorectal Work Group inaugural meeting is planned for the 28th October 2009.  The national bowel cancer team will attend this meeting.  Sumi Lolohea, General Surgeon will be the chair of the forum.

- Midland Lung Cancer Work Group has been established.

- A forum was held with interested parties to establish a Midland Consumer and Carer Reference Group on 21 September 2009.  Terms of reference and code of conduct have been agreed, with formal appointments to the group to be made in October.

- Planning has commenced to establish the Midland Supportive Care Work Group.  Graham Harbutt, Waikato/BOP Cancer Society will chair this forum.

- Planning has commenced to establish the Midland Research and Audit Work Group.  Chair of this group will be Professor Ross Lawrenson, Head of Waikato Clinical School of Medicine, University of Auckland.

- The Midland Cancer Network Strategic Plan 2009-2014 and annual work programme 2009-2010 was approved by the Midland DHB CEOs 7th August 2009 and distributed.

- Network manager provided a report and teleconferenced with the Midland DHB CEOs on the 7th August 2009.  In addition presented to the Midland GM planning and funding forum on the 2nd September 2009.

## Lung cancer

The aim is to improve access, waiting times and streamline the patient journey for lung cancer, focusing on service improvement activities to deliver measurable improvements from referral to first treatment.  The following summarises progress:

- The service and patient mapping work programme has been completed, the report on findings is due December 2009.  Findings were presented to the Executive Group in July 2009

- Work continues to progress on the recommendations made at the Midland Lung Cancer Work Group meeting on 23 July 2009.  Recommendations were to and progress to date include:

- ensure 100% patients diagnosed with lung cancer are discussed at regional chest conference – there has been an increase in patient numbers presented at chest conference, this will be reported in quarter two

- agree to regional work up guidelines and each speciality is to document their clinical pathway – an international document has been released regionally and this is currently been debated.   Establishment of a national lung cancer work group has commenced with first meeting planned for the 6th November. The Midland Cancer Network and Central Cancer Network clinical directors are chairing this first meeting

- agreement reached on regional performance indicators for access and timeliness – identified the need for the date of diagnosis.  The network has been able to gain more access to the national cancer registry and/or regional chest conference data.  The network aims to report against these indicators in quarter two

- investigating a fast track clinic for respiratory assessment for patients with suspected lung cancer.  Dr Denise Aitken, Lakes DHB is investigating fast track to CT.

- The MCN has sponsored two regional Lean Thinking training teams:

- general practitioner referral to respiratory first specialist assessment for suspected lung cancer

- streamlining the process of referral to regional chest conference (MDM) for lung cancer.

The purpose of sponsoring these two teams is twofold: utilise training to reduce wasted time and effort, standardise systems and processes, while improving patient care; and develop the cancer control workforce, promote regional networking and a regional and local continuous quality improvement culture within the Midland region.

Progress updates on these training teams is attached in the appendix.

## Bowel cancer

As previously mentioned the Midland Bowel Cancer Work Group is in the process of being established.  The first meeting is planned for 28th October 2009.  The national bowel cancer team will attend and present at this meeting.

The network is facilitating each area to complete the Ministry of Health national bowel cancer team colonoscopy questionnaire prior to the work group meeting - completed.

## Palliative care

A regional Liverpool Care Pathway (LCP) implementation planning and monitoring tool and annual report template have been developed for the Midland region’s LCP facilitators.  The national LCP office contributed to the development to these tools.  The benefit of these tools is to have regional consistency and share learnings.

Lakes DHB facilitated a Clinical Advisory Group – palliative care / end of life meeting 14th September 2009.  Agreements reached were:

- Rotorua Community Hospice Trust lead implementation of LCP into the medical wards Rotorua Hospital and one aged residential care organisation – this is dependant on identifying revenue to support this initiative

- identified that Rotorua Hospital would benefit from specialist palliative care consultant input.  The main issue was how Lakes would be funded for this enhancement to service.  A stepped and phased approach of four options was discussed; these need to be costed.

Taupo LCP Steering Group meeting was held 18th September 2009.

The Midland Cancer Network sponsored a Waikato Palliative Care Primary Gold Standards Framework Project and has entered into an agreement with Pinnacle Group Limited as the lead for this initiative.  Employment of a GP Liaison Palliative Care due to commence October 2009.

Waikato collaborative palliative care nursing working group continues – the main quality improvement initiative is the development of the Waikato palliative care directory for providers.

Midland specialist palliative care framework for generalist nursing and carer education has been endorsed and published.

## Midland non-surgical cancer treatment services

Refreshing and updating of the Midland Non-Surgical Cancer Treatment Services Plan (Barber, 2004) has commenced with radiotherapy services.

Adaptation of the Northern Cancer Network radiotherapy model has been utilised.  Progress to date includes:

- planning of cancer registration projections by type, and by DHB for the next twenty years

- identification of the number of linacs/assets required, and workforce requirements for next twenty years.  In addition started analysis on linac location scenarios for the region

- review of current radiotherapy capacity and efficiency levels against National Radiation Advisory Group, UK completed.

Midland chemotherapy chairs and nurse review project

Preliminary meeting with stakeholders has occurred to agree scope of project which will include safe environment, safe working limits, current and future demand, look at impact of new treatment regimes.  Development of project scope commenced.  This project will help inform the medical oncology component of the above plan.

## Reducing inequalities

While reducing inequalities is throughout all aspects of the network’s programme the following progress has been made:

- as previously mentioned planning to establish the Midland Supportive Care Work Group has commenced.  This group will oversee the development of the Midland supportive care services directory, a draft project plan has been developed in preparation for this group.  Agreement has been reached with the four regional cancer networks that wherever possible there will be consistency in approach when developing the directory

- discussions have commenced to look at the cultural competency framework and tools that are in place within each DHB

- a re-audit of Māori women with breast cancer treatment waiting times and identification of barriers to timely access to services has commenced.  Methodology has been agreed, population data collated and analysis commenced

- Māori Cancer Conference in August 2009 – two Midland Cancer Network staff presented at the conference and an additional three people from the network team attended.

Psycho-social assessment tool project

In June 2008 the Midland Cancer Network Executive Group approved a project to identify and test the value of an appropriate psycho-social assessment tool for cancer patients in the Midland.  The assessment tool was trialled with eighty participants (patients) who provided feedback as well as seven screeners (health professionals).  Findings were reported in the Midland Cancer Network Psycho-Social Assessment Tool Project Report (August 2009).

Midland PET-CT

The purpose of this service improvement initiative is to formalise and strive for regional standards and a transparent system and process for obtaining PET-CT scans for cancer patients.  Note: this project is to address current services.

The main reasons for the project were:

- confusion amongst stakeholders whether PET-CT scans were able to be ordered for patients, what the current clinical criteria is, the process to obtain approval and how the patient is supported through the process

- ensuring eligible patients and support persons had access to national transport and accommodation support

- inequity of access to appropriate clinical care

- regional lung cancer and regional non-surgical cancer treatment services work group meetings identified PET-CT as a service improvement priority.

Project progress to date includes:

- meetings held with all DHB stakeholders to clarify current situation

- clinical criteria agreed with all three DHB’s clinicians (this has been based on the Auckland criteria)

- identified national purchase unit code, clarified preferred provider with referral form, provider capacity, procedure and transport and accommodation costs, clarified ability to access to national transport and accommodation support if accessing Australian provider

- commenced development of a database to capture information to monitor and audit

- with DHB planning and funding identified budget holder in each DHB, price volume schedules, process for referral approval and process for transport and accommodation have been developed for each DHB

- an audit of the waiting time from referral to Pacific Radiology, Wellington for the region has commenced.

## Midland Cancer Network information system project

In December 2008 the Midland Cancer Network revised its original project scope and commissioned an international market scan of available information systems solutions that could meet the business requirements of the network.  The approach consisted of six activities:

- scope validation

- requirements validation

- perform a market scan and agree software sources for review

- perform due diligence on potential solutions

- determine a recommendation, if possible from among the identified candidates

- identify high level implementation considerations.

Eight international organisations were reviewed with two short listed: Somerset Cancer Registry England and QCOL, Queensland Australia.  A review of both systems was completed via video and/or web based conferencing.  The preferred recommended solution was the UK based Somerset Cancer Registry.  An end of project report, The Midland Cancer Network Information Systems Requirements & Options Validation Findings Report, was tabled and accepted in August/September 2009.

Work has continued with Somerset Health Informatics and the Sussex Cancer Network, England to gain further information in preparation to submitting a proposal to the Ministry of Health cancer service development fund.

## Adolescent / young adult cancer service plan

Key achievements for the quarter:

- enhancement of a database that captures the number of patients

For quarter 1: 15 new patients, 2 discharges and a total of 96 patients.

“Referrals to” include: Cancer Society, CanTeen, Child Cancer Foundation, dietician, district nurse, Fertility Associates, leukaemia and Blood Foundation, Medic Alert, True Colours, Wig Creations and social work

- Infection Alert card has been reviewed and updated, with the help of AYA consumers

- a new national adolescent and young adult cancer service logo has been developed with the help of Viscom at Waikato DHB and this will allow consumers to identify with the service more easily

- the service has sent letters to all general practitioners, advising them of the service and the support the AYA service is able to provide.  Positive feedback was received for keeping general practice in the loop

- A Long term Follow-Up Service for adolescent and young adult cancer survivors in the Midland area (Hudler, 2009) research project report has been received and will be considered.

## Midland research and audit sharing day

28th July Midland Cancer Network research and audit day was very successful with local clinicians presenting.  Professor Tony Blakley was the keynote speaker and he was ‘very impressed by what is happening and what people want to happen, some good research is going on in the region’. Professor Ross Lawrenson, Head of Waikato Clinical School of Medicine has agreed to be chair of the Midland research and audit work group.  The aim of the work group would be to direct and align research towards improving cancer outcomes and to link the regional cancer centre, University of Auckland and private sponsors (refer www.midlandcancernetwork.org.nz for presentations).

## Waikato prioritisation process

The Midland Cancer Network via the Executive Group supported the following proposals/business cases put forward/considered as part of the Waikato DHB prioritisation process:

- Waikato post radiotherapy dental treatment/dentures – approved $10,000.  needs to be tabled at regional GM planning and funding forum

- Waikato genitourinary cancer clinical nurse specialist 0.5fte – approved

- Waikato oncology pharmacist – declined – needs to go to a regional process to the Midland GM Planning and Funding forum, currently with Ruth Rhodes Waikato planning and funding

- Waikato elective services review for lung and bowel cancer – declined

- Waikato head and neck cancer clinical nurse specialist – not prepared and submitted – will try and get approved utilising current budget allocation

- Waikato regional cancer centre increased dedicated oncology social work and psychologist – currently with Ruth Rhodes Waikato planning and funding and awaiting response

- Waikato Māori cancer clinical nurse specialist/coordinator – Te Puna Oranga (Māori Health Service) put proposal on hold and therefore was not submitted

- Waikato gynae-oncologist business case – not prepared and submitted in time.

## Northern Cancer Network primary lung cancer research

The 21 DHBs, through DHBNZ have established a health research fund for the purpose of commissioning research that addresses key knowledge gaps for DHBs. The Northern DHB Support Agency Limited (NDSA – host institution) on behalf of Auckland and Counties Manukau DHBs, ProCare Networks Auckland and Manukau and Total Healthcare Otara and Northern Cancer Network (NCN) research proposal was accepted by the cancer research sub committee, with the proviso to include another regional cancer network and rural DHB.  The proposal title is Assessment of barriers to the early diagnosis of lung cancer within primary care.  Late March 2009 the Northern Cancer Network made a request that Midland Cancer Network and Lakes DHB be included within the research project.  The research project commenced 1 July 2009 and will last for three years.

Dr Denise Aitken is the local investigator for the research.  The research includes:

- clinical audit of all cases of primary lung cancer diagnosed in 2008

- interviews and focus groups with patients, whānau and GPs to explore possible barriers to healthcare access and early diagnosis

- identification of successful or innovative services

- comparison of findings with Auckland and Counties Manukau DHBs.

The Midland Cancer Network attended the hikoi ki Te Arawa on the 27th August to in Rotorua.

## National activities

Network manager represents the regional cancer networks on the New Zealand Cancer Control Steering Group.

The network clinical director and chair of the Midland Cancer Network Executive Group attend the New Zealand Clinical Advisory Group.

Midland network manager along with the clinical director of the Northern Cancer Network presented case study at the New Zealand Institute of Health Management on 17th September.  The theme of the conference was ‘networking, its all about relationships…’

Network manager attended national teleconference with Ministry of Health, Central Cancer Network and clinical director oral health to discuss provision and funding of dental prostheses post radiotherapy.  Issues were noted.

National lung cancer work group

The Midland Cancer Network clinical director along with the Ministry of Health and Central clinical director have been leading the development of a national lung cancer work group/network with the aim to establish national guidelines and standards for New Zealand.  The first meeting is planned for 6th November 2009.

Palliative care specialist palliative care service specifications

Continue to have input into the development of the national specialist palliative care service specifications.  The network manager (chair) and Tina Stacey Waikato planning and funding from the Midland region participate in this sub work group to develop the purchase units of the specifications.

The network where requested have supported organisations to input into the national gap analysis.

National consortium to develop national guideline implementation plans

In February 2009 a consortium (the New Zealand Guidelines Group [lead contract holder], the regional cancer networks [with Midland as lead], the Royal New Zealand College of General Practitioners, the Melanoma Network [MELNET], the Health Sponsorship Council and the Cancer Society of New Zealand) collaborated on a proposal for Guideline Implementation Plan Development and were successful as the preferred provider. The national guidelines involved are:

- Guidelines for the Management of Early Breast Cancer (published)

- Clinical Practice guidelines for the Management of Melanoma in Australia and New Zealand (published)

- Access and Referral (Suspected Cancer) Guidelines (published).

The Ministry of Health’s purpose in funding development of guideline implementation plans has been to disseminate and embed the guidelines throughout the sector.

Appendix

Regional Chest Conference Lean Thinking Project Scope and Update - 19 October 2009

| Project title: | Streamlining the process of referral to Chest Conference and reducing delays in the lung cancer journey |
| --- | --- |
| Project sponsor: | Jan Hewitt, Manager, Midland Cancer Network |
| Project team: | - Leonie Rauputu, Lung Cancer Clinical Nurse Specialist, Respiratory Service, Health Waikato - Gabby Reynolds, Clinical Nurse Manager, Ward 25, Health Waikato - Jenny Parry, Specialist Clinical Nurse Asthma/Respiratory - Tauranga Hospital - Margie Hamilton, Service Improvement Facilitator, Midland Cancer Network |
| Project purpose: | To improve the process of referral to the weekly regional Chest Conference at Waikato Hospital so that all referrals have all relevant documentation available for decision making at the next meeting |
| Project objectives: | Using lean thinking tools and methodologies: - identify the issues and barriers for referral to the weekly regional Chest Conference at Waikato Hospital - make recommendations and implement agreed improvements - 100% referrals have all relevant documentation by December 2009 |
| Project scope: | The key project investigation is the referral to the regional chest conference. This will be carried out in three phases. Phase 1 – Bay of Plenty DHB (completed by 1 October) Phase 2 – Lakes DHB Phase 3 - Waikato DHB Included in the scope is: - quality of the referral and supporting information received from the referring specialist - analysis of the number of re-discussions that impact on the capacity of Chest Conference |
|  | - participation in Chest Conference by Bay of Plenty, Lakes and Tairawhiti referring specialists |
| Project links: | Lung cancer is a national priority - 09/10 Midland Cancer Network work programme. |

Key project findings to date:

Phase 1 Bay of Plenty referrals

No referral guidelines or standard process for referrals - Each Bay of Plenty specialist uses a different process to refer to Chest Conference

Processing waste Time taken by lung cancer nurse specialists collating information from referral form and other sources to Chest Conference report form (one hour per referral or 4 weeks p.a.)

Reject waste Time spent by lung cancer nurse specialists trying to locate missing information and imaging (30 minutes per referral or 2 weeks p.a.)

Specialists do not refer all patients from Bay of Plenty. Concern expressed at time taken to complete referral form (1 hour) if information only to be entered in lung cancer database and not discussed at Chest Conference

Use of old Microsoft Word Chest Conference referral form (as only electronic option) - Waikato Forms Committee approved only a PDF version

Imaging or information not available in time for next Chest Conference. From April to August 2009 there were 16 (out of 23) weeks where imaging or information was missing. PACS may resolve imaging delays for Bay of Plenty. Impact is that the patient journey time is increased by 7 days

Recent action by Bay of Plenty private radiology provider to charge $100.00 for a CD copy of imaging for Chest Conference

Need to determine capability for private providers to upload digital files into Waikato/BOP PACS

Teleconference facility for out of area specialists to participate in Chest Conference is not utilised

General

Increasing numbers of re-discussions (post PET-CT, post surgery, post additional tests) 28% of patients reviewed from April – August 2009 were second or subsequent presentations at Chest Conference

PACS being implemented at Bay of Plenty and Waikato not compatible with Lakes

Concern raised that not all relevant Chest Conference discussion is captured on the Chest Conference Report

Chest Conference is 90 minutes and the number of patients discussed varies from 7 to 25. For the time period April to August 2009 Number on agenda; Number of occurrences; Time available for each discussion. <10; 6; 9 minutes. 11 - 15; 8; 6 minutes. 16 - 20; 8; 4.5 minutes. 21 - 25; 3; 3.6 minutes.

Unable to display Chest Conference Report and imaging simultaneously

Outcomes to date

- Team has a greater understanding of the complexity of the referral processes

- Way forward agreed in principle, particularly development of one form

- Improved service from Films on Loan

- Action in August by respiratory physicians to reduce re-discussions by requiring PET-CT to be done prior to referral to Chest Conference (too early to assess impact)

- Investigation into possible electronic referral form options with Viscom

- Discussion with private radiology provider regarding interface with Chest Conference.  Private providers require evidence of patient consent prior to transfer of diagnostic imaging

Next steps

- Map referral processes at Lakes and Waikato

- Further analysis of re-discussions by DHB and type (as requested by respiratory physicians)

- Consultation regarding content of new single electronic referral report (SERR) – acts as referral and Chest Conference Report

- Meet with Information Systems in each DHB to understand system capability and privacy/security requirements for the electronic options

- Development of electronic SERR - probably interactive Adobe form to designated email address or web-based form to database

- Review roles of administrator, CNS and respiratory physicians in Chest Conference preparation process

- Finalise Chest Conference Terms of Reference

- Develop information sheet for patients

- Develop guidelines and standard processes for referrals

- Monitor PACS implementation and interface with Lakes PACS

- Work with regional private imaging providers to facilitate timely access to private diagnostic imaging

- Investigate IT solutions to automate process e.g. agenda updated, referrals automatically generated to treatment services

- Investigate improved MDM facility including videoconferencing capability

Lung cancer GP referral to Respiratory FSA Midland Cancer Network - Lean Thinking Project Scope and Update

19 October 2009

| Project title: | Receipt of referral from GP to first specialist assessment (FSA) for suspected lung cancer. |
| --- | --- |
| Project sponsor: | Jan Hewitt, Manager, Midland Cancer Network. |
| Project team: | - David Boles – Nurse Specialist Cancer Care, Lakes DHB - Peng Voon – Business Leader Medical Services, Bay of Plenty DHB - Raewyn Jarvis-Hall, Clinical Nurse Manager, Hospice Waikato - Kay Berryman, Service Improvement Facilitator, Midland Cancer Network - Sharon Hardaker, Service Improvement Facilitator, Midland Cancer Network. |
| Project purpose: | To improve the percentage of patients who meet the 14 day benchmark for receipt of referral to FSA. |
| Project objectives: | Using Lean Thinking tools and methodologies: - identify the issues and barriers to meeting the 14 day benchmark from receipt of referral to FSA for suspected lung cancer - make recommendations and implement agreed improvements - improve the percentage by 20% from the baseline data (which was based on data from the period Jan 07 to June 08). Baseline Lakes 52% Target 72% BOP 30% Target 50% |
| Project scope: | The Lean thinking team represents a range of organisations. The key project investigation is the referral to FSA for suspected lung cancer. This will be carried out in 3 phases. Phase 1 – Lakes DHB Phase 2 – Bay of Plenty DHB Phase 3 - Waikato DHB Included in the scope is the quality of the referral received from the GP. Also, during the formal course time for Lean Thinking training a number of other sub activities have been undertaken. To date theses include: - 5S activities (to systematically clean and organise work areas) conducted at Hospice Waikato and Te Puna Oranga. - Queue reduction analysis and workload balancing at BOP DHB, medical services |
| Out of scope | - Processes prior to receipt of referral from the GP into the DHB are not included e.g. timing of (or issues for) patients presenting to GP with symptoms etc. - Processes that follow on from the FSA are not included e.g. preparation of referral to chest conference or treatment. |
| Project links: | 09/10 Midland Cancer Network Work programme. |

Key project findings to date:

Lakes DHB

| Issues | Opportunities |
| --- | --- |
| Multiple formats of referrals (phone, email, fax, letter) | Standardising the content and way referrals are sent by the GP would: - improve the chance of obtaining all required information - minimise number of places a referral can go to - reduce risk of losing a referral - speed up the journey of a referral |
| Quality of referrals variable Missing information, incorrect information/details | Audit to investigate if issues are general across all GPs/practices or specific to some, quality improvement by review of systems/template, communication with GPs |
| Multiple destinations for referral at the DHB | Single point of entry Less people handling each referral |
| Referrals reviewed once per week (Tuesday) | More frequent review of referrals |
| Comments: Lakes referral rate for suspected lung cancer is relatively low. In the period April to September 2009 10 referrals were received. This equates to a referral rate of 1.7 per month. This rate of referral is the same as for our baseline data (18 month period Jan 07 to June 08). Therefore, referrals to Lakes DHB have remained consistent. There is no issue with waiting lists for these types of referrals at Lakes. The two respiratory physicians are flexible in adding clinic appointments where required. There is a process in place for flagging of possible urgent cases to the specialists. Bronchoscopies are carried out on Thursday and Fridays so some forward planning is necessary. Again the number is low and generally no waiting time issues exist. There is good willingness to make changes / improvements at Lakes and staff have already, during the course of the project, initiated incremental improvements. In the period April to September 2009, eight out of 10 referrals were seen within 14 days (80%). Next steps – Lakes DHB: - Audit sample of referrals and discuss recommendations for improvements with the GP Liaison. - Consult with respiratory physicians on proposed changes to processing referrals within Lakes DHB, implement agreed changes and monitor outcomes. |  |

Proposed Process for Lakes:

Bay of Plenty – Queue analysis

Note: Queue analysis at Bay of Plenty DHB is for the respiratory service (not specifically lung cancer referrals). Summary: - As at end August there is a queue of 117 people at Tauranga Hospital. Five of those have been waiting >6months. - On average over the last year 47 referrals are accepted each month with only 35 being treated. - At the current rate of accepting referrals and treatment (and with current resources) the queue will continue to grow. - Takt time analysis indicates the following would be required to clear the current queue in 6 months: - an average of 31 referrals seen each month (15 of those new referrals / 16 off the queue) - a patient needs to be seen every 40 minutes (FSA) by each of the respiratory physicians After six months when the queue is significantly reduced an average of 31 new referrals could be received per month.

Capacity/wk(hrs)

20

Weekly Demand

Capacity/wk(mins)

1200

FSA

15

600

min

FU

15

300

min

Left(for backlog)

300

min

Backlog

117

FSA

4680

FU

2340

Total

7020

Wks2clear

23.4

or 6 months