| Project Details |  |
| --- | --- |
| Project Title | Midland Cancer Network Supportive Care Service Directory Project |
| Project Sponsor | Midland Cancer Network Manager |
| Project Manager | Graham Harbutt, Waikato/BOP Cancer Society |

| Document Control |  |  |  |
| --- | --- | --- | --- |
| Plan compiled by | Jan Hewitt |  |  |
| Version Number | Draft 3 | Date | 27 October 2009 |
| Associated documents | Midland Cancer Network Strategic Plan 2009 – 2014, August 2009 Midland Cancer Network 2009/10 Work Programme, August 2009 |  |  |

| Definitions |  |
| --- | --- |
| Background to project | This project is in response to: - clinical staff identified a lack of knowledge and inadequate level of supportive care services for cancer patients and their family/whānau (Lakes DHB cancer control workshop, 2007) - patients have limited access or knowledge of all the support services that are available - New Zealand Cancer Control Strategy Action Plan Goal 4, Objective 2 Action 68 - Guidance for Improving Supportive and Rehabilitative Care for Adults with Cancer in New Zealand (draft, 2009) - a Ministry of Health funded cancer control implementation project report on a national cancer psychological services stocktake 2005-2006 (Surgener, et al, 2006) that indicated that there are inequalities for the Midland region compared to other parts of New Zealand in terms of access for patients and the level of psychological services. |
| Project Goal(s) | To develop a cancer supportive care services directory for the Midland Cancer Network area. |
| Project Objectives | - To develop a Midland Cancer Network supportive care service directory available in hard copy and electronically - To have accessible information on what, where and how to access supportive care services within the Midland Cancer Network |
| Coverage | Supportive care services related to cancer control within the Midland Cancer Network area (Bay of Plenty, Lakes and Waikato) |

| Stakeholders |  |  |  |  |
| --- | --- | --- | --- | --- |
| Key stakeholders: | - Midland Cancer Network Executive Group - Midland Cancer Network Supportive Care Work Group - Midland Cancer Network Consumer and Carer Reference Group |  |  |  |
| Other stakeholders | - Waikato DHB - Bay of Plenty DHB - Lakes DHB - Cancer related non-government organisations, including Māori and Pacific NGOs - Primary Health Organisations - Northern, Central and Southern Cancer Networks |  |  |  |
| Key Constraints | - Midland Cancer Network budget constraints - Midland Cancer Network management resource constraint due to recent resignation |  |  |  |
| Project Approach and Management |  |  |  |  |
| Project approach | - A collaborative approach with stakeholders in the development of the supportive care services directory. - Wherever possible there will be consistency in approach with the other New Zealand regional cancer networks. - A template will be developed to capture the information electronically from stakeholders wherever possible. - Adopt and adapt the directory format from international cancer networks. - Build on current information we have, i.e. stakeholder database. |  |  |  |
| Project structure | - Sponsor, Jan Hewitt Manager, Midland Cancer Network - Midland Cancer Network Executive Group (Steering group) - Midland Supportive Care Work Group will provide expert guidance - MCN Consumer and Carer Reference Group will provide consumer input |  |  |  |
| Project start date | October 2009 | Project completion | January 2010 |  |
| Financial summary | The project costs will be meet by the Midland Cancer Network Network organisations will support this initiative by contributing time and information to the project |  |  |  |
| Milestones |  |  |  | Date |
| Midland Cancer Network Supportive Care Work Group established terms of reference agreed, key stakeholders identified |  |  |  | November 2009 |
| Review and design of supportive care services templates Template distributed to stakeholders |  |  |  | November 2009 |
| Identify and implement supportive care services directory website requirements Consultation on draft supportive care services directory |  |  |  | December 2009 |
| Midland Cancer Network supportive care services website is go live and Midland Cancer Network supportive care services hard copy is published and distributed |  |  |  | January 2009 |

| RISKS AND RISK MANAGEMENT |  |  |  |
| --- | --- | --- | --- |
| Risks | Probability (low, med, high) | Impact (low, med, high) | Risk management strategy |
| Lack of engagement | Low | High | Effective and appropriate communication and coordination with key stakeholders |
| Stakeholders expectations exceed available resource | Medium to High | High | - Project plan Open and transparent communication |
| Lack of consensus | Low | High | Encourage feedback and participation. |

| AUTHORISATION |  |  |  |
| --- | --- | --- | --- |
| Project Sponsor | Jan Hewitt | Date |  |