Midland Cancer Network 2009-10 Work Plan & 2008-09 Progress Report

# Executive Summary

This report summarises the Midland Cancer Network 2009-10 work plan and reports on 2008-09 progress.

The Midland Cancer Network has a leadership, facilitation and coordination role in bringing together and working with stakeholders across organisational and service boundaries to:

- reduce the incidence and impact of cancer;

- reduce inequalities with respect to cancer; and

- improve the experience and outcomes for people with cancer.

The Midland Cancer Network 2009-10 work plan supports the Minister’s priority to improve cancer waiting times and aligns with the national cancer control work programme 2009-10 priorities as well as the Midland Cancer Network Strategic Plan 2009-2014.

| What we intend to do (objective) | How we’ll get there (actions) | Target / Indicator / Milestone |
| --- | --- | --- |
| To foster clinical leadership | - establish regional lung & colorectal work groups |  |
| To improve access, waiting times and streamline the patient journey for bowel and lung cancer, focusing on service improvement activities to deliver measurable improvements; - from referral to first treatment for lung and bowel cancer | - complete lung cancer patient/service mapping quality improvement report by December 2009 - complete colorectal patient / service mapping work programme and quality improvement report by June 2010 - complete two LEAN thinking training team projects: GP referral to respiratory FSA and regional chest conference by Dec. 2009 - develop a regional colonoscopy capacity planning and demand management framework by June 2010 - develop MDM framework for lung and bowel cancer | Report baseline waiting times quarter 4 to Ministry of Health on: - Time from referral to first treatment for lung and bowel cancer (excludes inpatients and acutes) by DHB and ethnicity - Proportion of lung and bowel cancer patients accessing MDM by DHB and ethnicity |
| To reduce inequalities along the cancer continuum | - develop Midland Cancer Network supportive care services directory by June 2010 | Regional service directories developed by 2014 as per network strategic plan |
|  | - explore implications of implementing Suspected Cancer in Primary Care: Guidance for Referral and Reducing Disparities Guidelines for lung and bowel cancer within existing resources by June 2010 - actively participate in NZGG national guidelines implementation plan project by March 2010 | Suspected cancer in primary care guidelines implemented by 2014 as per network strategic plan for lung, bowel, breast, prostate |
|  | - re-audit Maori women with breast cancer treatment waiting times and identify barriers to timely access to services, Jun 2010 |  |
|  | To improve and increase access to budget PET-CT scans based on clinical need through agreed; - regional standardised clinical criteria - regional decision making process flow including access to transport and accommodation for patient and support person - monitoring framework | Increase access for eligible Midland cancer patients to PET-CT scans (within budgeted volumes) |
| To improve regional planning and support national cancer treatment health target | - to refresh and update the Midland Non-Surgical Cancer Treatment Services Plan (2004) by June 2010 - to scope Midland chemotherapy chairs and nurses future requirements by June 2010 | Support health target reducing cancer wait times for radiation and medical oncology |
| To promote regional planning and improve access to palliative care | - Support continued rollout of end of life Liverpool Care Pathway - Scope joint regional opportunities between Waikato and Lakes | Evidence based best practice Promote regional planning |

This is the second Midland Cancer Network progress report.  2008-09 key achievements include:

- development of the Midland Cancer Network Strategic Plan 2009-2014, including publication of An Assessment of Cancer Health Needs in the Midland Cancer Network Region: 2009

- relocation of the network team to a single location at 198 Pembroke Street, Hamilton.

- Midland Cancer Network website developed – www.midlandcancernetwork.org.nz and quarterly Koha O Mātauranga newsletters

- continued to develop the Midland Cancer Network team, infrastructure, consumer participation and supporting national initiatives

- work towards addressing inequalities through a review of Maori, Pacific and refugee and new migrants governance and participation structure, stocktake of Māori providers and services and review of the Action Plan inequalities recommendations

- lung cancer service and patient mapping baseline information completed  and participated in 3rd regional lung cancer conference

- facilitated regional implementation of the specialist palliative care end of life care programme – Liverpool Care Pathway (LCP)

- development of a specialist palliative care nursing education framework for generalists, including gap analysis

- hosted Deborah Murphy from NHS Institute of Palliative Care to present on end of life programme tool the Liverpool Care Pathway and participate in regional planning

- published the Midland Adolescent and Young Adult Oncology Haematology Service Report and Action Plan 2008-2010 (November 2008) with work progressing towards achievement of the recommendations

- development, pilot and evaluation of a psycho-social assessment tool for Midland

- sponsored a regional Lean Thinking training team to increase colonoscopy capacity

- facilitated and supported Lakes DHB to be included in the Northern Cancer Network primary lung cancer research proposal to investigate possible differences in access to healthcare services between Auckland, Counties Manukau and Lakes DHBs

- Midland Cancer Network as part of consortium with New Zealand Guidelines Group was successful with Ministry of Health request for proposals to develop national implementation plans for three new national guidelines (breast, melanoma, access and suspected cancer in primary care).

# Contents

Executive Summary	1

Introduction	4

Vision	4

Principles	4

Governance structure	5

2009/10 work plan	6

Network resources	6

Reporting on progress	7

2008-09 Progress report	10

Midland Cancer Network Strategic Plan 2009-2014	11

Network website and newsletter	11

Midland Cancer Network infrastructure development	11

Network addressing inequalities work programme	13

Lung cancer service and patient mapping work programme	13

Midland Palliative Care Work Group	14

Midland Breast Cancer Work Group	15

Midland AYA Cancer Services Work Group	15

Midland Cancer Network information systems project	17

Midland psycho-social assessment tool project	17

Lean Thinking colonoscopy training team	17

Northern Cancer Network primary lung cancer research proposal	18

National guidelines implementation plan project	18

Waikato cancer control key achievements	18

BOP cancer control key achievements	21

BOP cancer control key achievements	22

Lakes DHB cancer control key achievements	23

Appendix one – Midland Cancer Network management team	24

Appendix two – Midland Cancer Network management team work plan 2009-10	25

# Introduction

This is the second annual report of the network that details the networks annual work plan activities for 2009-10 then highlights 2008-09 key achievements.    The development of the Midland Cancer Network work plan for the 2009-10 year has been informed by priorities signalled by the Minister, Ministry of Health and the Midland Cancer Network Strategic Plan 2009-2014.

The Midland Cancer Network is one of four regional cancer networks established in New Zealand to facilitate a number of the initiatives contained in the New Zealand Cancer Control Strategy Action Plan 2005-2010.  The Midland Cancer Network area encompasses the following three District Health Board (DHB) regions: Bay of Plenty, Lakes and Waikato with an open invitation to Taranaki and Tairawhiti.

## Vision

The network’s vision is improved cancer control through increased regional collaboration not constrained by organisational, service or professional boundaries.

The network has a leadership, facilitation and coordination role in bringing together and working with stakeholders to:

- reduce the incidence and impact of cancer;

- reduce inequalities with respect to cancer; and

- improve the experience and outcomes for people with cancer and their family/ whānau through the complex pathway of care.

## Principles

Core principles to guide the network’s structure and function include:

- a person centred approach

- ensuring timely and equitable access to cancer control services

- recognising and respecting cultural diversity

- promoting a seamless patient pathway across the cancer control continuum

- services being of high quality

- being effective and evidenced based

- being sustainable

- ensuring a multidisciplinary team approach

- ensuring a continuous quality improvement approach

- taking a partnership approach with stakeholders, actively engaging health professionals, Māori, Pacific peoples, non-government organisations, consumers, carers and communities

- undertaking service improvement within the context of a planned, co-ordinated, collaborative and integrated approach.

The network adds value by taking a regional population-based approach to engage and involve stakeholders, influence and support decision making to enable health gain attainments beyond what stakeholders could achieve alone.

## Governance structure

The Midland Cancer Network continues to evolve.  The network governance via the Executive Group and the network management team have been implemented and work has commenced on development of the clinically led work groups.  Work groups established include service specific and tumour specific for the following:

- non-surgical cancer treatment services					- care coordination

- palliative care								- breast cancer

- adolescent and young adult cancer services 				- lung (in progress)

This report firstly outlines the 2009-10 work plan priorities, initiatives and indicators and the second section describes the Midland Cancer Network’s 2008-09 key achievements.

# 2009/10 work plan

The development of the Midland Cancer Network work plan for 2009-10 year has been informed by priorities signalled by the Minister, and the Ministry of Health.   The Cancer Control Programme is an integrated national programme that covers the Ministry of Health, DHBs’ and regional cancer networks’ activity across the cancer continuum to implement the New Zealand Cancer Control Strategy and associated Action Plan.  The national Cancer Control Work Programme (2009, draft) reflects these priorities and provides context:

- Regional cancer networks’ priority signals include:

- lung and bowel cancer – regional cancer networks are to initiate 2-3 service improvement projects ahead of the completion of detailed service mapping work programme

- focus on non-surgical cancer planning and regional access to cancer surgery.

- DHBs’ signals include:

- focus on cancer as a priority area continues

- focus on priority cancers – bowel and lung

- improving access to cancer treatment and improving wait times, both surgical and non-surgical, with a focus on vulnerable groups and poorer performing DHBs

- continue working with regional cancer networks on the development and implementation of surgical and non-surgical service improvement initiatives

- cancer health target: radiotherapy wait times

- Wait times indicators: POP 10 chemotherapy, surgical (national work required to develop surgical indicator)

- DHB capital (e.g. linear accelerator) planning, workforce (linking to broader workforce projects) and information systems (e.g. development and implementation of national project with initial focus on data definitions) planning, but needs to happen within the context of regional and national work

- palliative care – boost hospice funding initiative, ongoing development of specialist service specifications and gap analysis.

The Midland Cancer Network strategic directions are to:

- share knowledge and information to enable informed decision making

- facilitate regional service quality improvement leading to better, sooner, more convenient services

- support innovation and infrastructure development to reduce inequalities and build capacity and capability.

## Network resources

The Midland Cancer Network is funded via a crown funding agreement variation with Waikato DHB for $550,000 per annum to 30 June 2011.   The network has 6.6 fte to support the Midland Cancer Network and Waikato palliative care work programme (appendix one).

## Reporting on progress

The Midland Cancer Network will report on the 2009-10 priorities.  Utilising the Midland Cancer Network’s measuring success framework a set of indicators has been developed for 2009/10 to measure progress.  It is noted that development of cancer control indicators is evolving and that current information systems may not have the capability to capture events.  2009-10 will be a development and set-up year.

Midland Cancer Network is required to report progress to the Ministry of Health quarter two and an annual report on progress via the Waikato DHB DAP reporting process.  These reports, along with information for stakeholders on Midland Cancer Network activities, are available on the Midland Cancer Network website www.midlandcancernetwork.org.nz

The 2009-10 work plan focus is on three priority areas to make demonstrated improvements to people within Midland.

What this work plan means for people

Cancer control requires a collaborative approach with multiple stakeholders to make a difference to ensure that the actions taken over 2009-10 aim to provide people with better, sooner, more convenient cancer services.  The following table describes what will be done for people and who is taking led on different aspects of the work.

| What will be done… | Led by |
| --- | --- |
| There will be an increased likelihood of your cancer being detected earlier: - primary care doctors will be given more guidance on how to identify suspected cancer - planning will occur on referral for suspected lung & bowel cancer - more people will be screened through the cervical and breast screening programmes | - the Ministry is leading the development of these guidelines which are due to be released November 2010 - Midland Cancer Network stakeholders - DHBs and BreastScreen Midland |
| You will have better access to high quality treatment: - more patient cases for lung and bowel cancer will be discussed at multidisciplinary team meetings - waiting time standards will be developed for lung and bowel cancer patients - the lung and bowel cancer treatment pathways will be developed and improved so people are diagnosised and treated within recommended guidelines - capacity for colonoscopy services will be reviewed to improve access to this service - when your doctor recommends a PET scan, improved and equal access including transport and accommodation support | - Midland Cancer Network stakeholders - Midland Cancer Network / DHBs / Ministry of Health - Midland Cancer Network stakeholders / work groups - Midland Cancer Network stakeholders / colorectal work group - Midland Cancer Network stakeholders / DHBs |
| Your wait times for cancer treatment services will be improved: - further action will be taken to reduce wait times for radiotherapy through meeting the national wait time target - review and refresh the Midland non-surgical cancer treatment services plan (2004) to identify resource requirements to meet the future service demand - wait time standards will be developed for chemotherapy and surgery | - Regional cancer Centre, Waikato DHB - Midland Cancer Network stakeholders - Ministry of Health / DHBs |
| You will be supported in your end of life care so that your care is delivered in the most appropriate setting for you: - more funding will be provided to hospices to improve the services - service specifications for specialist palliative care services will be finalised - develop a LCP roll out plan for outstanding areas - look at opportunities to increase access to specialist palliative care services for Lakes people | - Ministry of Health / DHBs - Ministry of Health - Midland Cancer Network and Lakes and BOP DHBs - Midland Cancer Network, Health Waikato and Lakes DHB |

The following summarises the Midland Cancer Network 2009-10 work plan objectives, tasks and indicators.

| What we intend to do (objective) | How we’ll get there (actions) | Target / Indicator / Milestone |
| --- | --- | --- |
| To foster clinical leadership | - establish regional lung and colorectal work groups | Work groups established |
| To improve access, waiting times and streamline the patient journey for bowel and lung cancer, focusing on service improvement activities to deliver measurable improvements; - from referral to first treatment for lung and bowel cancer | - complete lung cancer patient/service mapping quality improvement report by December 2009 - complete colorectal patient/service mapping work programme and quality improvement report by June 2010 - complete two Lean Thinking training team projects: GP referral to respiratory FSA and regional chest conference by Dec. 2009 - develop a regional colonoscopy capacity planning and demand management framework by June 2010 - develop MDM framework for lung and bowel cancer by June 2010 | Report baseline waiting times quarter 4 to Ministry of Health on: - Time from referral to first treatment for lung & bowel cancer (excludes inpatients and acutes) by DHB and ethnicity - Proportion of lung and bowel cancer patients accessing MDM by DHB and ethnicity |
| To reduce inequalities along the cancer continuum | - develop Midland Cancer Network supportive care services directory by June 2010 | Regional service directories developed by 2014 as per network strategic plan |
|  | - explore implications of implementing Suspected Cancer in Primary Care: Guidance for Referral and Reducing Disparities Guidelines for lung and bowel cancer within existing resources by June 2010 - actively participate in NZGG national guidelines implementation plan project by March 2010 | Suspected cancer in primary care guidelines implemented by 2014 as per network strategic plan for lung, bowel, breast, prostate |
|  | - re-audit Maori women with breast cancer treatment waiting times and identify barriers to timely access to services, Jun 2010 |  |
|  | To improve and increase access to budget PET-CT scans based on clinical need through agreed; - regional standardised clinical criteria - regional decision making process flow including access to transport and accommodation for patient and support person - monitoring framework | Increase access for eligible Midland cancer patients to PET-CT scans (within budgeted volumes) |
| To improve regional planning and to support national cancer treatment health target | - to refresh and update the Midland Non-Surgical Cancer Treatment Services Plan (2004) by June 2010 - to scope Midland chemotherapy chairs and nurses future requirements by June 2010 | Support health target reducing cancer wait times for radiation and medical oncology |
| To promote regional planning and improve access to palliative care | - Support continued rollout of end of life Liverpool Care Pathway - Scope joint regional opportunities between Waikato and Lakes | Evidence based best practice Promote regional planning |

For further detail refer to the Midland Cancer Network management team plan in appendix two.  The 2009-10 work plan builds on progress to date.

# 2008-09 Progress report

This section reviews the network’s key achievements for 2008-09 as well as highlights from Bay of Plenty, Lakes and Waikato stakeholders.

The Midland Cancer Network 2008-09 key achievements include:

- development of the Midland Cancer Network Strategic Plan 2009-2014, including publication of An Assessment of Cancer Health Needs in the Midland Cancer Network Region: 2009

- relocation of the network team to a single location at 198 Pembroke Street, Hamilton.

- Midland Cancer Network website developed – www.midlandcancernetwork.org.nz and quarterly Koha O Mātauranga newsletters

- continued to develop the Midland Cancer Network team, infrastructure, consumer participation and supporting national initiatives

- completion of Midland Cancer Network addressing inequalities project phase one

- lung cancer service and patient mapping baseline information completed

- commenced regional implementation of the specialist palliative care end of life care programme – Liverpool Care Pathway (LCP)

- development of a specialist palliative care nursing education framework for generalists, including gap analysis

- hosted Deborah Murphy from NHS Institute of Palliative Care to present on end of life programme tool the Liverpool Care Pathway and participate in regional planning

- Midland Cancer Network Information Systems project commenced December 2008 to identify information solutions to support the network work programme

- published the Midland Adolescent and Young Adult Oncology Haematology Service Report and Action Plan 2008-2010 (November 2008) with work progressing towards achievement of the recommendations

- development, pilot and evaluation of a psycho-social assessment tool for Midland

- sponsored a regional Lean Thinking colonoscopy training team to increase capacity and development of an 2009-10 action plan

- facilitated and supported Lakes DHB to be included in the Northern Cancer Network primary lung cancer research proposal to investigate possible differences in access to healthcare services between Auckland, Counties Manukau and Lakes DHBs

- Midland Cancer Network as part of consortium with New Zealand Guidelines Group was successful with Ministry of Health request for proposals to develop national implementation plans for three new national guidelines (breast, melanoma, and suspected cancer in primary care).

These initiatives are briefly discussed.

## Midland Cancer Network Strategic Plan 2009-2014

The Midland Cancer Network Crown Funding Agreement required the network to develop a strategic plan by 30 June 2009.  To support the planning process Population Health (Health Waikato) collated the three districts’ health needs assessment information related to cancer control into one document  - An Assessment of Cancer Health Needs in the Midland Cancer Network Region: 2009.

In addition a regional and inequalities review of the New Zealand Cancer Control Strategy Action Plan goals one to six was completed.  This information along with significant engagement of stakeholders resulted in the first Midland Cancer Network Strategic Plan 2009-2014.

## Network website and newsletter

The Midland Cancer Network communication plan (2008) identified the complexity of communicating and information sharing with multiple stakeholders. The objective was to develop a website and produce quarterly newsletters.

A website was developed in partnership with the network team, visual communications, Waikato DHB and DigitalStream and went live March 2009.  The contractual agreement and content concept was shared with other New Zealand networks.  The website describes the function and form of the network, Midland cancer control services, progress to date and annual initiatives and publication of resources.  A key feature is ‘Your Health’ section with high level information and links intended to promote healthy lifestyles to people within Midland Cancer Network stakeholder organisations.

Go to www.midlandcancernetwork.org.nz for further information.

In November 2008 the inaugural quarterly newsletter Koha O Mātauranga (means sharing knowledge) was sent to stakeholders.  The newsletter provides brief local, regional and national updates to the wider stakeholder groups as well as profiling stakeholder organisation and/or their initiatives.

## Midland Cancer Network infrastructure development

The network management team

A key achievement was the relocation of the network team to a single location to 198 Pembroke Street, Hamilton.

The network management team (appendix 1) has had a number of changes in the last year.  Claudia Romano, administrator went on maternity leave and has been replaced by Jenna Arnel.  Margie Hamilton and Kay Berryman have been appointed as service improvement facilitators.  The network also entered into an arrangement with Business and Costing Solutions Limited to provide analytical support.

In addition the network has responsibility for the Waikato Palliative Care Operations Network and the associated work programme and has employed Sharon Hardarker as service improvement facilitator. Recruitment is in progress for a GP Liaison – palliative care with both positions on a fixed term basis.  Progress specifically related to Waikato palliative care has not been included in this document.

Team members have been allocated a portfolio for the network work groups with roles and responsibilities.   The network sponsored one regional Lean Thinking training team which included one network management team member.

In September 2008 the Ministry of Health sent a team to visit Scotland and England cancer networks.  New Zealand regional cancer network managers and clinical directors made up the team.  The purpose was to fast track learning regarding the establishment and development of regional networks.  Learning and resources from the site visit have been shared with Midland stakeholders.  Since the visit strong links have been formed with international networks.  The Midland Cancer Network hosted a site visit from the Sussex Cancer Network and the Institute of Palliative Care, England.

This year has seen greater alignment between the national cancer team and the regional cancer networks.  The network manager represents the regional cancer networks on the New Zealand Cancer Control Steering Group.  The network’s clinical director and the Waikato DHB Chief Operating Officer (chair of the Midland Cancer Network Executive Group) are on the Clinical Treatment Advisory Group.  The network also participates on the New Zealand Regional Cancer Network Forum.  The network manager is also on the national palliative care service specification work group, chair of the palliative care service specification purchase unit work group, member of the DHBNZ/HRC cancer research group and network lead for the New Zealand Guideline Implementation Plan project (discussed later in report).

The network on request has presented to various forums, e.g. Ministry of Health, Cancer Control Council, National Bowel Cancer team, Midland Elective Services team, Whakatane Management Journal Club, Health Waikato Advisory Committee (Board sub-committee) National Oncology Nurse Conference, Long Term Systems Framework Clinical Networks Project.  In addition network stakeholders were supported to participate in the Patient Management Framework workshop with Victorian State Government and the Ministry of Health and the launch of the national melanoma guidelines.  The network manager and clinical director also participated in the first ever cancer control prioritisation workshop facilitated by the Ministry of Health cancer team.

The Midland Cancer Network Executive Group

The Midland Cancer Network Executive Group continues to meet monthly via teleconference with quarterly face to face meetings.  Membership continues to evolve and strengthen (appendix 1).

The network work groups that report to the Executive Group include the Midland:

- Non-Surgical Cancer Treatment Work Group

- Palliative Care Work Group

- Care Co-ordination Forum

- Adolescent / Young Adult Cancer Services Work Group

- Breast Cancer Work Group

- Lung Cancer Work Group (in progress)

- Colorectal Work Group (in progress)

- Psycho-social Assessment Tool Project Work Group.

Consumer/carer participation

The network’s Consumer and Carer Participation Framework and action plan (2008) aims to support developing collaborative partnerships and ensure the active involvement of consumers and carers in cancer control service improvement across the Midland area.  The following action plan recommendations have been achieved:

- Midland Cancer Network executive and work group consumer and carer representatives position descriptions and code of conduct

- implementation of system and processes for the Payment Policy for Stakeholders Consultation and Participation

- website recruitment of consumers and carers with a range of opportunities to be involved

- developed and facilitated consumer representative orientation

- supported two consumers to attend the national consumer training workshop

- facilitated patient and whānau interviews to gain perspectives of the lung cancer pathway.

## Network addressing inequalities work programme

The following project objectives have been completed which include:

- Maori, Pacific and refugees and new migrants governance structure and participation framework

- stocktake of Maori health providers and services

- review of the Midland DHBs’ health needs assessment with respect to cancer control

- stocktake of national, regional and local inequalities research

- review of the New Zealand Cancer Control Strategy Action Plan 2005-2010 55 inequalities recommendations.

Findings from the phase one project have informed the Midland Cancer Network Strategic Plan 2009-2014 and the annual work programme.

## Lung cancer service and patient mapping work programme

Patient and service mapping is a comprehensive approach to capture and understand the patient’s whole journey, establish what, how and where services are delivered and who provides the services, identify key issues and gaps in service for the patient and the service providers across the continuum, and identify opportunities for service improvement.  All of this information has been collated and will be presented to the Midland Cancer Network Lung Cancer Work Group in July 2009, then summarised into a quality improvement plan.

The 3rd regional Lung Cancer Conference was held at Waikato Hospital, 10 November 2008.  The Midland Cancer Network presented the role and functions of the network and preliminary findings to date.  The four regional priorities for focus were:

- the need for regional lung cancer work group

- improve access to PET-CT scan services

- increase access to the regional Chest Conference

- timely access to thoracic surgery.

The first three priorities have been identified in the network’s 2009-10 work programme.  The lung cancer work group chair has been appointed and draft terms of reference have been developed.  The Midland Cancer Network has commenced work to streamline the PET-CT scan process.  There was confusion about whether DHBs funded PET-CT or not and as a result of confusion there was inequity of access.  Work in progress includes regional agreement on clinical criteria; streamline process to procedure including transport and accommodation, authorisation process, clarification of price volume schedule and reporting and monitoring framework.  This work will continue into 2009-10.

## Midland Palliative Care Work Group

In 2007/07 the Ministry of Health released funds to DHBs to support and commence implementation of the new components of the draft specialist palliative care service specifications (2008, Ministry of Health).  Regional collaboration was recommended within the crown funding agreement to DHBs.  The Midland Cancer Network Palliative Care Forum agreed to focus on:

- implementation of the Liverpool Care Pathway and;

- the development of a Midland specialist palliative care nursing education framework and resource for generalists.

The Midland Cancer Network manager in addition sponsors the Waikato Palliative Care Operations Network and has a service level agreement linked to this programme.  Waikato has been implementing Liverpool Care Pathway for the last three of years.  The network sponsored a one off Waikato extension of the Liverpool Care Pathway implementation for Hospice Waikato and specialist nursing resource to develop the education framework and plan for generalists.

From a Midland perspective lead Liverpool Care Pathway facilitators have been appointed in BOP and Lakes DHB to commence implementation.     Midland Cancer Network arranged for Theresa Mackenzie, Arohanui Hospice, national Liverpool Care Pathway Lead to facilitate a Midland Liverpool Care Pathway facilitator’s foundation day in August 2008.  Planning and implementation commenced following this session.

Two regional workshops were held with specialist palliative care nurses and as a result a Midland specialist palliative care education framework and plan for generalist has been developed.

In addition a Midland regional palliative care planning day hosted Deborah Murphy from NHS Institute of Palliative Care to present on Liverpool Care Pathway and participate in regional planning forum.

## Midland Breast Cancer Work Group

The Midland Early Stage Breast Cancer Mapping Report and Action Plan 2007-2010 summarises the patient and services, issues and opportunities for improvement.  The first Midland Breast Cancer Work Group met in November 2008.  Mr. Ian Campbell was nominated as chair and terms of reference agreed.

Unfortunately early 2009 the network lost a team member that had responsibility for the Breast Work Group, and as a result progress has been slow.  Progress to date includes:

- BreastScreen Midland held workshops and developed a 2009-10 action plan to improve Māori and Pacific women breast screening rates.  The draft action plan is out for consultation at the time of publishing this report

- Planning to audit Māori breast cancer women wait times between the critical steps of the pathway has commenced.  It is planned that for those women that had long waits a chart audit for reasons will completed

- Re-audit of the stereotactic biopsy identified further work was required to embed the Lean Thinking project process redesign changes.

Stereotactic biopsy audit

A further retrospective audit of stereotactic biopsies undertaken at the Breast Care Centre (Waikato Hospital) for out of area women over an eight month period was completed.  This was follow-up of a 2008 regional Lean Thinking improvement project.  The average waiting time has been reduced by four days. However, the audit shows that the 14 day target between referral and procedure proposed in the Lean Thinking project was achieved for only five (36%) of patients.  The target waiting time may be reached and maintained if the improvements identified in the project are implemented fully. Discussions have resumed with providers and staff involved to get outstanding improvements implemented.

It was noted that network requires support and leadership from the Executive Group, other stakeholders and providers of cancer health care services to ensure sustainable service improvements are fully implemented. It was agreed that the regional work groups should be actively involved to ensure successful implementation of improvements.

## Midland AYA Cancer Services Work Group

Key achievements for 2008-09 include:

- service to patients commenced November 2007

- the Midland Adolescent and Young Adult (AYA) Oncology Haematology Service Report and Action Plan 2008-2010 was published November 2008

- the AYA patients have had increased access to the clinical nurse specialist – note: 2007-08 partial year

| AYA CNS patient numbers | 2007-08 | 2008-09 |
| --- | --- | --- |
| Active patients | 33 | 75 |
| New registrations | 33 | 50 |
| Discharges | 1 | 7 |

The following pie chart demonstrates the various methods of AYA patient contacts and by ethnicity during 2008-09.

Other achievements include:

- the Midland AYA Cancer Service Work Group was established to lead the implementation of the action plan and support the clinical nurse specialist as the service develops

- lead adult clinicians were identified and each has an advisory role to the AYA Work Group and clinical nurse specialist

- Waikato paediatric shared care nurse appointed

- the paediatric and AYA clinical nurse specialist nurses are developing an integrated framework of roles and responsibilities e.g. cover for leave

- development of the multidisciplinary team has commenced at Waikato focusing on quality improvement, networking and improving continuity of care for inpatients and outpatients

- AYA clinical nurse specialist attends adult MDMs as required

- Contact is made with Starship monthly to inform adult clinicians of current and recently opened clinical trials

- AYA education programme implemented, including holding a Midland AYA study day

- Ward 25 Waikato hospital inpatient survey to identify needs to enhance youth friendly environment while an inpatient

- AYA database to record the clinical nurse specialist patient information

- the establishment of the Midland Adolescent Young Adult Cancer Service was nominated as a finalist in the Waikato Best of Health Awards 2008 (this is further discussed later in the report).

## Midland Cancer Network information systems project

Data and information is the biggest challenge for the network and supporting clinical governance.  The information systems project commenced December 2008 as a result of findings from the breast cancer care coordination database work.  The network has identified five levels of information requirements.

The network’s information requirements include:

- population based planning information

- organisation/service based information

- patient management framework information (project focus)

- sector and network surveillance and monitoring information

- information dissemination and knowledge.

The key level to support the clinical work groups is the patient management framework information.  The objectives of the project were to complete a market scan of available information system solutions that can meet the network patient management framework information business requirements, including review of the Somerset Cancer Registry System and make recommendations on the preferred option including implementation implications.

The network, in partnership with Waikato DHB Chief Information Officer, employed Simpl to manage the project.  A report will be presented to the executive group July / August 2009.

## Midland psycho-social assessment tool project

Supportive care encompasses the essential services required to meet the physical, social, cultural, emotional, nutritional, informational, psychological, spiritual and practical needs throughout a person’s experience with cancer.  The Midland Cancer Network psycho-social assessment tool project aim was to reduce the impact of cancer by better meeting the psycho-social needs of cancer patients through development of a psycho-social assessment tool.  The project objectives were to:

- adapt or adopt a psycho-social assessment tool for the Midland Cancer Network area

- pilot the assessment tool

- evaluate and monitor the tool and ability to complete referrals to current and available support services.

The psycho-social assessment tool was successfully piloted and recommended for full implementation.

## Lean Thinking colonoscopy training team

An opportunity arose to sponsor a regional team to undertake Lean Thinking training October 2008 to March 2009.  The team mapped the colonoscopy pathway from general practitioner referral to colonoscopy procedure for Midland DHBs.  Key issues identified were demand and capacity both for colonoscopy procedures and outpatient clinics, variation and issues with managing general practitioner referral forms, different grading systems between specialists and DHBs.

A number of opportunities for improvement were identified.  Project outcomes included awareness of local hospital pathways and issues; understanding regional variation in practice; information on wait lists is now made available for planning and monitoring and Waikato general surgeons have increased capacity by an additional two procedures per week.  Further work will continue as a priority in 2009-10.

## Northern Cancer Network primary lung cancer research proposal

The Northern Cancer Network approached Midland Cancer Network and Lakes DHB to participate in a DHBNZ/Health Research Council research proposal that is investigating possible differences in access to healthcare services between Auckland, Counties Manukau and Lakes DHBs.  The research will investigate differences between stage at diagnosis, time from referral to diagnosis and barriers to access. The approach will involve clinical audit, interviews with patients and focus groups with GPs. An outcome of the research will be the identification of successful or innovative services.  The project timeframe is three years and will commence July 2009.  The Midland Cancer Network will support both Lakes and the Northern Cancer Network as required within available resources.

## National guidelines implementation plan project

The Midland Cancer Network (lead regional cancer network) and along with a consortium of organisations (Cancer Society, MelNet, Health Sponsorship Council and College of General Practitioners) with New Zealand Guidelines Group as contract holder, were successful with request for proposals to develop national implementation plans for three new national guidelines (breast, melanoma, suspected cancer in primary care guidelines).  It should be noted at the time of this report only one of these guidelines has been published – melanoma. Planning has started and development of the implementation plans will occur in 2009-10.

## Waikato cancer control key achievements

- Lean Thinking project team to improve paediatric length of day stay for chemotherapy at Health Waikato

- Waikato DHB Best of Health Awards 2008 – four finalists in these awards held in November have a direct impact on the cancer continuum in Midland.  They were:

- Double balloon enteroscopy - This innovative procedure was commended in the excellence in treatment category at the National Innovation Awards and won the innovation section in the Waikato Best of Health Awards. This pioneering new procedure is reducing the need for surgery, cutting the waiting time for diagnosis and reducing the length of time a patient spends in hospital. A double balloon enteroscopy enables doctors to view and take samples of a patient's small bowel, allowing them to diagnose cancers and other causes of intestinal bleeding without performing invasive surgery. 70% of patients receive a diagnosis and for 30% the procedure shows that they have no disease of the small bowel thus avoiding the need for more invasive surgery in order to make a diagnosis.

- Adolescent and Young Adult Oncology Haematology Service - A finalist in the continuous improvement for clinical service delivery section.  This new service reflects an innovative approach to meet the needs of those aged 14-24 who have cancer. The youth friendly model of care provides care coordination, advocacy, education and support to adolescents and young adults and their families.

- Nurse-led clinic – breast cancer care, support and assessment - A finalist in the continuous improvement for clinical service delivery section.  This new clinic aims to ensure women and their families feel supported, informed and receive optimal care during the breast cancer journey. Invitations go to women with breast cancer referred by a surgeon to the Waikato Hospital oncology department to attend a clinic where they can meet with a breast cancer nurse specialist to discuss the impact of cancer and treatment on their lives, explore their understanding of treatments available and alleviate any fears or misconceptions. Feedback from women has been positive.

- Hepatitis C management in the prison setting – A finalist in the collaboration section.  Prisoners are a key risk group for transmission of hepatitis C with a rising prison population and up to 25% carrier rate. Waikato Hospital Hepatitis Clinic worked closely with prison management and two senior prison nurses to develop this shared care model that enabled prisoners to receive their full treatment in the prison setting thus increasing the rate of cured infections, reducing the transmission rate and the potential for cancer.

- breast screening for eligible Maori women is not achieving the national target. BreastScreen Midland facilitated workshops to identify across the breast screening continuum, activity that is happening well, activity that could be improved upon, activity that is not happening and needs to occur.  The Midland Cancer Network participated in this forum.  The information was gathered from key stakeholders and was used to develop the action plan for 2009-10.  The action plan focuses on enhancing Māori recruitment, enhancing enrolment and booking process for Māori women and enhancing Māori participation

- A Midland HEHA review of the Māori and Pacific health providers’ workforce training needs analysis was completed to identify areas to increase collaboration to build the workforce.  In addition the Midland HEHA DHBs will host a food industry pilot project manager to work with food industry and Midland stakeholders on national and regional initiatives.

## Regional cancer centre has:

- developed a video commentary for patients that are planning to undergo radiation therapy.  The video commentary includes an introduction and virtual walk through the department and information related to simulation and radiation treatment

- had success in recruitment and retention of critical clinical staff

- appointed and developed the gynae-oncology (0.5 fte) and colorectal (1.0 fte) cancer clinical nurse specialists roles to support and facilitate coordination of care for complex patients

- Health Waikato Clinical Board approved an advanced care planning pilot project that supports end of life care preferred priorities of care tool.  The pilot project will commence 2009-10

- provided over 3200 radiotherapy treatments for other non-Midland DHBs in 2008-09

- installed an Image Guided Radiotherapy process to improve the accuracy of the radiation field placement, and to reduce the exposure of healthy tissue during radiation treatments

- installed respiratory gating technology to synchronize delivery of radiation with the patient's own respiratory cycle. The technique allows treatment with a high dose of radiation to cancerous tumors while sparing a larger volume of healthy tissue

- improved software for dosimetry allowing more effective and efficient radiation calculation dose to a location

- introduced pharmaceutical funding for herceptin and oxaliplaton

- radiation oncology continues to track positively within the 6 week target

- medical oncology although improving still has issues in relation to the BOP staffing situation. The regional cancer centre assistance has and will continue to be provided, a locum medical oncologist is due to start in September 2009.

## BOP cancer control key achievements

2008-09 key achievements for include:

- opening of the new Cancer Centre in Tauranga in September 2008

- haematologist appointed from mid May 2009, resulting in a positive impact for at least 100 new and follow-up patients during this time. Inpatients are also benefiting from having the haematologist on-site. The specialist is now doing selected bone marrow biopsies for both inpatients and outpatients. These activities have reduced travel for patients and improved clinical outcomes.

- increased access and equity in relation to PET-CT scans. In the absence of a national purchase unit and IDF arrangements, Midland DHBs are in the process of agreeing regional access criteria for PET-CT scans.

- 97% performance success relative to cancer waiting time targets.  Additional efforts have been made by all specialists to ensure waiting times for medical oncology are within guidelines

- development and trialing of a psycho-social assessment tool. The findings of this trial were published in June 2008 and will help inform service planning in 2009/2010. Alerted to the level of local need prior to the trial, BOPDHB has approved funding for increased psycho-social support services

- participation in the 2009 Cancer Control Council Cancer Care Experience of Patients Accessing Treatment Survey

- closer working relationship between BOPDHB and Waikato DHB to ensure equity of access for cancer patients

- completion of the Liverpool End of Life Pathway pilot project between BOP and hospices.  Closer relationship between the hospices and secondary services including clarity of roles and support.

Focus for 2009-2010 include:

- appointment of a second locum medical oncologist  from September 2009 for six months

- cancer waiting times managed within six week requirement

- minor skin lesion surgery devolved to the primary sector

- improve journey for patients with lung cancer

- improve journey for patients with colorectal cancer

- completion of the Lean Thinking training for a number of staff involved in streamlining the patient journey.

## Lakes DHB cancer control key achievements

2008-09 key achievements for include:

- the Northern Cancer Network approached Lakes DHB via the Midland Cancer Network to participate in DHBNZ/Health Research Council research that is investigating possible differences in access to healthcare services between Auckland, Counties Manukau and Lakes DHBs

- appointment of clinical nurse specialist Māori cancer care

- established HPV vaccination team

- continued support to Te Kahui Hauora pilot project

- commenced introduction of an end of life programme with implementation of the Liverpool Care Pathway in Taupo

- development and trialing of a regional psycho-social assessment tool.

Focus for 2009-2010 include:

- Northern Cancer Network and Lakes DHB lung cancer research initiative

- cancer waiting times managed within six week requirement

- improve journey for patients with lung cancer

- completion of the Lean Thinking training for a number of staff involved in streamlining the patient journey for lung cancer

- increased access and equity in relation to PET-CT scans. In the absence of a national purchase unit and IDF arrangements, Midland DHBs are in the process of agreeing regional access criteria and processes for PET-CT scans

- improve journey for patients with colorectal cancer.

# Appendix one – Midland Cancer Network management team

| Network Team | Role | Full Time Equivalent |
| --- | --- | --- |
| Dr Charles De Groot | Clinical Director | 0.2 |
| Jan Hewitt | Manager | 1.0 |
| Loryn Scanlan | Service Improvement Manager | 1.0 |
| Caleb Lewis | Service Improvement Manager | 1.0 |
| Margie Hamilton | Service Improvement Facilitator | 1.0 |
| Kay Berryman | Service Improvement Facilitator | Casual up to 0.2 |
| Jenna Arnel | Administrator / PA | 1.0 |
| Darryl Groufsky | Analyst | 0.2 minimum (outsourced) |
| Total |  | 5.6 fte |
| Waikato Palliative Care |  |  |
| Sharon Hardarker | Service Improvement Facilitator – Waikato | 1.0 fixed term until 30/6/10 |
| Vacant | GP Liaison – palliative care – Waikato | 0.6 – 1.0 fixed term until 30/6/10 |
|  |  | 1.6 fte |

# Appendix two – Midland Cancer Network management team work plan 2009-10

The following objectives link to the Midland Cancer Network Strategic Plan 2009-2014.  The shaded areas indicate that these objectives will work towards addressing inequalities.  The work plan focuses on:

- improving access, waiting times to improve diagnosis and treatment of lung and bowel cancer

- improving access to supportive care

- reviewing and refreshing the Midland non-surgical cancer treatment services plan

- continuing to support work groups – AYA, breast, non-surgical cancer treatment, palliative care, care co-ordination

- regional planning and development of palliative care services

- development of Midland Cancer Network infrastructure.

1. Service Quality Improvement Priority – Improve diagnosis and treatment of priority cancers - lung cancer

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 2.1 Promote clinical governance for lung cancer | Establish MCN Lung Cancer Work Group - terms of reference developed - prioritise recommendations - develop protocols, oversee CQI initiatives | Improve wait times from referral to first treatment for lung cancer - Report to Ministry Quarter 4 Increased and equity of access to PET-CT - Bi-annual reporting of volumes by DHB and by ethnicity Number of lung cancer patients presented at MDM by DHB by ethnicity - Report to Ministry Quarter 4 | Jul 2009 ongoing | C. De Groot L. Scanlan & MCN Lung Work Grp |
| 2.2 Service/patient mapping work programme to develop quality improvement plan | Complete service and patient mapping lung cancer report with CQI and reducing inequalities recommendations |  | Sept 2009 | L. Scanlan |
| 2.3. Implementation of best practice PMF, clinical guidelines and standards | Stocktake and review of Suspected Cancer in Primary Care recommendations for lung cancer Explore implications and opportunities for lung cancer within available resources |  | Jun 2010 | C. Lewis |
| 2.4 Regional quality improvement initiatives to improve patient care and reduce inequalities for lung cancer | Sponsor two regional Lean Thinking training teams - GP referral to respiratory FSA - Referral to regional chest conference |  | June – Nov 2009 | Regional teams |
| 2.4.1. Improve access to diagnostic services 2.4.2.1. PET-CT | Agree clinical criteria for region Define and documented decision making process Develop reporting and monitoring tool Ensure PUC, price, volume schedule in place for each DHB |  | June 2010 | J. Hewitt D. Groufsky |
| 2.5 Promote development of MDT & improve continuity of care | Complete stocktake of current situation Develop MDM criteria & framework Improve MDM access within available resources |  | June 2010 Quarter 4 | M. Hamilton |
| 1.5.3 Participate & support NCN primary lung cancer translational research proposal that includes Lakes DHB | Within available resources provide support as required |  | 2009-2012 | J. Hewitt L. Scanlan D. Groufsky |
| 3.2 Develop regional cancer control workforce framework and plan | Identify current services within each DHB that support developing cultural competency within the cancer workforce Identify gaps and opportunities within available resources |  | Dec 2009 June 2010 | C. Lewis |
|  | Identify current and future workforce requirements for lung cancer |  | June 2010 | L. Scanlan C. Lewis |

2. Service Quality Improvement Priority – Improve diagnosis and treatment of priority cancers - bowel cancer tumour stream

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 2.1 Promote clinical governance for colorectal cancer | Establish MCN Colorectal Cancer Work Group - terms of reference developed - prioritise recommendations - oversee CQI initiatives | Improve wait times from referral to first treatment for bowel cancer - Report to Ministry Quarter 4 Number of colorectal cancer patients presented at MDM by DHB by ethnicity - Report to Ministry Quarter 4 | Dec 2009 Ongoing | C. Lewis |
| 2.2 Service/patient mapping work programme to develop quality improvement plan | Complete colorectal service/patient mapping and reducing inequalities work programme Publish findings with CQI recommendations |  | June 2010 | L. Scanlan |
| 2.3. Implementation of best practice PMF, clinical guidelines and standards | Stocktake and review of Suspected Cancer in Primary Care recommendations for bowel cancer Explore implications and opportunities for bowel cancer within available resources |  | June 2010 | C. Lewis |
| 2.4 Regional quality improvement initiatives to improve patient care and reduce inequalities for bowel cancer | Develop and undertake capacity and demand planning model with the aim to increase colonoscopy services |  | June 2010 | J. Hewitt C. Lewis D. Groufsky |
| 2.5 Promote development of MDm & improve continuity of care | Complete stocktake of current situation Develop MDM criteria & framework |  | June 2010 Quarter 4 | M. Hamilton D. Groufsky |
| 3.2 Develop regional cancer control workforce framework and plan | Identify current and future workforce requirements for bowel cancer |  | June 2010 | L. Scanlan C. Lewis |

3. Improve regional planning of Midland non-surgical cancer treatment services

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| Support achievement of national cancer health target – radiation and medical oncology | Review and update the Midland NSCTS Plan (2004). Refresh data, review and update plan focusing on medical and radiation oncology services. Continue to facilitate and support the MCN NSCT work group and associated initiatives. |  | Ongoing June 2010 | L. Scanlan J. Hewitt D. Groufsky |
|  | Review regional chemotherapy chair and nurse requirements for the future |  | June 2010 | M. Hamilton |

4. Improve regional planning of palliative care services

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| Promote & develop regional palliative care planning & services for Waikato & Lakes DHB | Scope Lakes DHB provider arm specialist palliative care service requirements and implement opportunities as resources allow |  | June 2010 | J Hewitt S Hardarker |
| 2.4.5 Best practice palliative care end of life programme | Continue to facilitate and support the MCN Palliative Care Work Group and associated initiatives Continue to support implementation of the LCP across Midland Scope opportunities to implement the reflective data cycle tool. Continue to support implementation of the Midland nursing education framework for generalists. Actively participate in the national development of the specialist palliative care service specifications, purchase units and reporting requirements | Midland LCP implementation plan developed - Increase the number of Midland organisations that have implemented EoL LCP | June 2010 | J. Hewitt |

5. Service Quality Improvement – improve access to supportive care information and services

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 1.3.3 Develop and maintain a Midland supportive care service directory | Develop a MCN supportive care service directory Establish MCN Supportive Care Work Group - chair appointed - terms of reference agreed | Midland supportive care directory published raising health professional and public awareness of service available - 100% of service directories developed by 2014 | June 2010 | C. Lewis |
|  | Stocktake current cancer supportive care services within Midland |  |  |  |
|  | Publish Midland supportive care service directory |  |  |  |
| 2.3. Implementation of best practice PMF, clinical guidelines and standards | Stocktake and review of Guidance for Improving Supportive & Rehabilitation for lung and bowel cancer Explore implications and opportunities for lung and bowel cancer within available resources |  | tbd | C. Lewis |

5. Service Quality Improvement – improve access and waiting times for breast cancer

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 2.1.1 Continue to support Breast Work Group | MCN Breast Cancer Work Group meets Work group prioritises service improvement initiatives related to the Midland Early Stage Breast Cancer report and Improvement Plan (2008) within available resources |  | Ongoing | M.Hamilton MCN Breast Work Group |
| Improve wait times for Māori breast cancer women | Identify barriers and improve waiting time access to critical stages of the breast cancer pathway for Māori women Re-audit waiting times against standards Identify barriers and opportunities to improve |  | Dec 2009 | K. Berryman |
|  | Improve process flow to stereotactic biopsy Re-audit waiting times against standards | Achieve stereotactic biopsy wait time of 14 days | Mar 2010 | L. Scanlan |
| 1.4.3 Promote & support implementation of the Early stage breast cancer guideline | When published disseminate to network stakeholders Make guideline available on MCN website Include availability in MCN quarterly newsletter Agenda to MCN Breast Cancer Work Group |  | Aug 2009 | M. Hamilton & MCN Breast Cancer Work Group |
| Support BSM to achieve national target | Support BSM action plan to increase Māori and Pacific screening rates |  | ongoing | C. Lewis |

6. Service Quality Improvement - AYA

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 2.1.1 Continue to support AYA Cancer Services Work Group | Work group meets and works on service improvement initiatives related to the Midland AYA OHS report and Improvement Plan (2008) within available resources |  | Ongoing | M.Hamilton MCN AYA Cancer Work Group |

7. Midland Cancer Network infrastructure development

| What we intend to do (objective) | How we will get there (actions) | Milestones / Outcomes / Indicator | Timeframe | Who will do the work |
| --- | --- | --- | --- | --- |
| 2.1 Promote clinical governance for major tumour and service work groups | Establish MCN Genitourinary Cancer Work Group - terms of reference developed |  | June 2010 | C. Lewis |
|  | Facilitate MCN research and audit day Based on evaluation establish MCN research and audit work group Develop research & audit resource on website |  | July 2009 June 2010 | K. Berryman |
| 3.6 Build IS capacity for regional planning, audit, monitoring & evaluation | MCN IS sector/market scan project completed Explore opportunities to utilise the national Business Objects Intelligence Tool sitting on top of the Cancer Datamart (incorporates NZ Cancer Registry and other data collections) Develop a MCN database for regular audit and reporting requirements |  | Aug 2009 June 2010 | J. Hewitt J. Hewitt D. Groufsky |
| Implement the MCN communications plan recommendations | MCN continues to develop and refine an operation framework that describes the functions and form of how the network will accomplish the strategic goals, objectives & service requirements |  | June 2010 | M. Hamilton J. Arnel |
|  | MCN actively participates in the National Māori Cancer Conference and identifies opportunities for information sharing and service improvement |  | Sep 09 | C. Lewis K. Berryman |
|  | Quarterly Koha O Matāuranga email newsletters with MCN including stakeholder contributions/ updates disseminated to stakeholders |  | Aug 09 Nov 09 Feb 10 May 10 | J. Arnel |
|  | Implement website password protected area Develop website research & audit resource |  | Aug 09 | M. Hamilton K. Berryman |
| 1.5.5 Jointly lead & facilitate annual national cancer control conference with other RCN and MoH | Participate in developing conference themes, speakers Assist with facilitation and administrative support as required with conference |  | Jun 2010 | J Hewitt, MoH & NZ RCNs |
| 1.4 Disseminate & promote national & regional guidelines & pathways | Actively participate in NZGG consortium agreement to develop national implementation plan for Melanoma, Breast and Suspected Cancer in Primary Care (note dependant on publication of guidelines) |  | Mar 2010 | J. Hewitt |
| 1.5.4 Support Oranga Tane Maori joint research proposal | Within available resources provide support as required for the three year research proposal |  | 2009-2012 | All |

The Midland Cancer Network area includes the Bay of Plenty, Lakes and Waikato district health board regions with an open invitation to Tairawhiti and Taranaki.

19 February 2009, Minister’s 2009 expectation letter to DHBs – examples include: cancer health target - radiotherapy wait times, increase elective volumes, foster clinical leadership, improved regional and national planning

25 March 2009, D. Woodley letter to DHBs and regional cancer networks

Ministry of Health and DHB DAP workshop 20 February 2009

Please note: refer to DHB district reporting for full cancer control report on progress

Bay of Plenty, Lakes and Waikato districts