Midland Cancer Network

6 monthly report July – December 2009

This report provides information about progress against the Midland Cancer Network Annual Work Plan 2009/10 for 1 July – 31 December 2009.  Please note section two work plan has been updated to include the National Cancer Control Work Programme Plan 2009-2010 objectives and reporting requirements (these are highlighted in blue).

Section 1: Summary of key activities and outputs for this period

Collaboration in action is evidenced by the number and range of regional stakeholder meetings/teleconferences facilitated by the team this period:

- Midland Executive Group – Jul / Aug / Oct / Nov

- Midland Palliative Care Network – Dec

- Midland Non-Surgical Cancer Treatment Services Work Group – Sept / Dec

- Midland Care Coordination/CNS Work Group – Sue Hayward, Director of Nursing accepted the chair position – Aug / Nov

- Midland Lung Cancer Work Group –  Jul

- Midland AYA Cancer Services Work Group – Jul / Nov

- Waikato Palliative Care Operations Network – Jul / Aug / Oct / Nov / Dec.

The following regional work groups were established:

- Midland Colorectal Work Group – inaugural meeting held October with appointment of Mr Sumi Lolohea as chair.  National bowel cancer team have attended and presented twice over this period

- Midland Research and Audit Work Group – July a workshop was held with local clinicians presenting.  Professor Tony Blakley was the keynote speaker.  As a result of the day Professor Ross Lawrenson, head of Waikato Clinical School of Medicine was appointed chair.  The Work Group had its first meeting November.  The aim of the work group is to direct and align research towards improving cancer outcomes and to link the regional cancer centre, University of Auckland and private sponsors.

- Midland Consumer and Carers Work Group – an establishment meeting was held in September.  Appointment of members to the work group has occurred; terms of reference and code of conduct have been completed.

- Midland Supportive Care Work Group – inaugural meeting held December with appointment of Graham Harbutt, Cancer Society as chair, agreed terms of reference and work programme.

Midland Cancer Network Strategic Plan 2009-2014 and Annual Work Plan 2009/10 were developed and endorsed by stakeholders and Midland DHB CEOs August 2009. The plans were provided to the Ministry of Health as required in the regional cancer networks Crown Funding Agreement.

MOH Cancer Service Development Funding was secured to support the following Midland Cancer Network projects:

- Midland Cancer Network lung and bowel cancer elective services review  ($50K)

- Midland Cancer Network Lean Thinking training teams (2) – lung and chemotherapy initiatives ($50K)

- Improve early detection of lung cancer ($30K)

- Midland Cancer Network Somerset Cancer Registry feasibility study ($90K)

- New Zealand regional cancer network’s Maps of Medicine pilot project – lung cancer ($90,775)

Total revenue of $310,775 excl gst.  Quarter 3 will see commencement of these initiatives following agreement and signing of Crown Funding Agreements.  All initiatives, except for the Lean training teams and lung and bowel elective service review will extend into the 2010-11 year.

Other approved Midland service development initiatives include:

- Rotorua Hospice LCP Implementation into Rotorua Hospital, the network assisted with this initiative

- He Hikoi he Manaaki Tangata: a journey caring and supporting people – Te Puna Oranga, Waikato DHB

- Improving palliative care outcomes for rural Mâori palliative care patients, Hospice Eastern Bay of Plenty.

Lung cancer – several initiatives are in progress:

- service and patient mapping and baseline information on waiting times has been completed.  A draft report on findings is out for consultation quarter 3.

- the Midland Lung Cancer Work Group has agreed that 100% of patient diagnosed with lung cancer will be discussed at the regional chest conference; each speciality agree regional work up for patients with non-small cell lung cancer (in progress); agreement reached on regional indicators to be developed over time (in progress); investigate fast track pathways; Lakes DHB investigate straight to CT pathway (in progress).

- Network sponsored and completed two Lean thinking training teams (refer to appendix for summaries) for:

  - GP referral to respiratory FSA for suspected lung cancer

  - Streamlining the process of referral to regional chest conference

- First draft lung cancer indicators report is found in appendix (note indicators still under development).

Bowel cancer – as mentioned above the Midland Colorectal Work Group has been established and the network facilitated completing the national bowel cancer team colonoscopy stocktake questionnaire.

The work group agreed the annual work programme of mapping the pathway from referral to hospital treatment and retrospective audit of waiting times between key stages.  Project scope developed awaiting clinician signoff.   Data requirements for audit completed including request for cancer registry and laboratory information.  Mapping will occur in two stages, unlikely to achieve initial timeframe of June 2010 due to ambitious work plan and loss of personnel.

Non-surgical cancer treatment services – refreshing and updating the Midland Non-Surgical Cancer Treatment Services Plan (Barber, 2004) has commenced with radiotherapy services.  The first draft plan is out for consultation/presented to stakeholders and plan due for completion June 2010.

Palliative care - several initiatives have been completed or are in progress:

- developed regional LCP implementation planning and monitoring tool and annual report template for the Midland LCP facilitators.  The national LCP office was asked to comment on the tools. This will enable consistency of approach and a regional view of progress and better enable sharing of learnings.

- framework and process for implementing the LCP Reflective Data Cycle has been endorsed for Waikato this will be shared with other LCP facilitators in quarter 3.

- agreement of approach to undertake regional palliative care strategy planning, to commence in quarter 3

- Lakes DHB Clinical Advisory Group – palliative care/end of life group meetings were held in September.  Agreements reached were:

  - Rotorua Community Hospice lead implementation of LCP into medical wards Rotorua Hospital and one aged residential facility – funding obtained via service development fund and implementation has begun

  - identified Rotorua Hospital would benefit from specialist palliative care consultant input.  Issue is funding, a stepped and phased approach will be included in the Lakes component of the palliative care strategy plan.

- Taupo/Turangi implementation of LCP continues with LCP Steering Group meeting held September

- the Midland Cancer Network sponsored a Waikato Palliative Care Primary Gold Standards Framework project and entered into an agreement with Pinnacle Group Limited as the lead for this initiative.  A GP Liaison palliative care was employed October, but resigned November; therefore the project has discontinued at this point in time.

- Waikato Palliative Care DSL Review (2006) and the Waikato Collaborative Palliative Care Review (2006) recommendations have all been completed.  The Waikato Nursing Work Group for this period has completed the following:

  - review and update of the care communication record (patient held record for palliative care in the home)

  - Hospice Waikato, Waikato Hospital palliative care service and Health Waikato district nursing service jointly developed a shared service pamphlet for patients and family/whanau with a new Waikato district palliative care brand and look

  - developed a Waikato palliative care directory of services including:

    - documented all referral process flows and access to out of hours support

  - clarified the DSL criteria and process for accessing palliative care carer relief and respite care and implemented a new application form

- Midland Specialist Palliative Care for Generalist Nursing and Carer Education Framework (2009) has been endorsed and published.  The annual education calendar has been posted on network website and distributed.

Psycho-social assessment tool project – In June 2008 the Midland Cancer Network Executive Group approved a project to identify and test the value of an appropriate psycho-social assessment tool for cancer patients in the Midland.  The assessment tool was trialled with eighty participants (patients) who provided feedback as well as seven screeners (health professionals).  Findings were reported in August in the Midland Cancer Network Psycho-Social Assessment Tool Project Report (August 2009).

Midland PET-CT initiative – the purpose of this service improvement initiative was to formalise and strive for regional standards and a transparent system and process for obtaining PET-CT scans for cancer patients.  The main reasons for the initiative were:

- confusion amongst stakeholders whether PET-CT scans were able to be ordered for patients, what was the current criteria, the process to obtain approval and how the patient is supported through the process

- ensuring eligible patients and support persons had access to national transport and accommodation support

- inequity of access to appropriate clinical care

- Midland Lung Cancer and Non-Surgical Cancer Treatment Work Groups identified PET-CT as a service improvement priority.

Progress to date includes:

- meetings held with all DHB stakeholders to clarify current situation

- clinical criteria agreed with all three DHB clinicians (will need to review in light of recent Ministry PET-CT correspondence December 2009)

- identified national purchase unit code, clarified preferred provider with referral form, provider capacity, process for transport and accommodation, clarified the ability to access national transport and accommodation support for accessing an Australian provider (if required)

- developed and implemented simple spreadsheet in all DHBs to capture information to monitor and audit

- with DHB planning and funding identified budget holder in each DHB, price volume schedules, process for referral approval and process for transport and accommodation within each DHB

- an audit of waiting time from referral to Pacific Radiology, Wellington for the region.

First draft network indicator of PET-CT volumes is found in the appendix of this report (note indicator under development).

## Midland Cancer Network information system project – In December 2008 the Midland Cancer Network revised its original project scope and commissioned an international market scan of available cancer information system solutions that could meet the business requirements of the network.  The approach consisted of six activities:

- scope validation

- requirements validation

- perform a market scan and agree software sources for review

- perform due diligence on potential solutions

- determine a recommendation, if possible from among the identified candidates

- identify high level implementation considerations.

Eight international organisations were reviewed with two short listed: Somerset Cancer Registry England and QCOL, Queensland Australia.  A review of both systems was completed via video and/or web based conferencing.  The preferred recommended solution was the UK based Somerset Cancer Registry.  An end of project report; The Midland Cancer Network Information Systems Requirements & Options Validation Findings Report, was tabled and accepted in August/September 2009.  Work has continued with Somerset Health Informatics and the Sussex Cancer Network, England.

This initiative will now move to the feasibility phase under the Ministry of Health cancer service development fund.

Joint initiative between the Ministry of Health and the four regional cancer networks has meant that the networks have an agreement enabling access to the New Zealand Cancer Registry data and other database information to assist with planning, monitoring and reporting.

## Adolescent/young adult cancer service (AYACS) - key achievements include:

- Infection Alert card has been reviewed and updated, with the help of AYA consumers

- a new national adolescent and young adult cancer service logo has been developed

- AYACS Waikato hospital oncology ward booklet developed

- the service has sent letters to general practitioners of AYA patients, advising them of the service and the support the AYA service is able to provide.  Positive feedback was received for keeping general practice in the loop

- A Long term Follow-Up Service for adolescent and young adult cancer survivors in the Midland area (Hudler, 2009) research project report has been received and will be considered.

- enhancement of a database that captures the number of patients and type of support they may require;

| 2009-2010 | Quarter 1 | Quarter 2 |
| --- | --- | --- |
| Number of new patients | 14 | 13 |
| Number of discharges/deaths | 2 | 5 |
| Total patients at end of quarter | 95 | 103 |

Referrals were made to a wide range of health and social service providers.  For the six month period there were 256 phone calls, 152 texts and 256 face to face visits.

Māori breast cancer service waiting times

A Maori Breast Cancer report is currently underway with detailed analysis completed for Waikato, Lakes and Bay of Plenty. This audit follows recommendations outlined in the Midland Early Breast Cancer Patient Mapping 2007-2010 where audit of waiting times required further activities for:

- improving the cancer workforce understanding of ethnic and other inequalities in cancer

- ensuring Māori and Pacific participation at all levels of network decision making and in the planning, developing and implementing of service initiatives

- investigating and supporting targeted cancer-related initiatives for Māori and Pacific people

- improving access to patient information that is culturally effective

- improving access to supportive care to address the needs of Māori and Pacific patients and their families.

Waikato prioritisation process – The Midland Cancer Network Executive Group supported proposals as part of the Waikato DHB prioritisation process.  Approved were:

  - Waikato post radiotherapy dental treatment/dentures ($10K)

  - Waikato genitourinary cancer clinical nurse specialist (0.5 fte).

## National activities

Network manager represents the regional cancer networks on the New Zealand Cancer Control Steering Group.

The network clinical director and chair of the Midland Cancer Network Executive Group attend the New Zealand Cancer Advisory Group.

Midland network manager along with the clinical director of the Northern Cancer Network presented case study at the New Zealand Institute of Health Management on September.  The theme of the conference was ‘networking, its all about relationships…’

Network manager attended national teleconference with Ministry of Health, Central Cancer Network and clinical director oral health to discuss provision and funding of dental prostheses post radiotherapy.  Issues were noted.

Network manager, clinical director and service improvement manager attended a presentation hosted by the University of Auckland and the NZGG on the Map of Medicine (UK).

Network manager and COO attended a Ministry of Health Cancer Control Strategic Planning day in December.

National lung cancer work group

The Midland Cancer Network clinical director along with the Ministry of Health and Central Cancer Network clinical director have been leading the development of a national lung cancer work group/network with the aim to establish New Zealand lung cancer pathway/guidelines and standards.  The first meeting was held 6th November 2009.

## Palliative care specialist palliative care service specifications

Continue to have input into the development of the national specialist palliative care service specifications.  The network manager (chair) and a Waikato planning and funding person participate in a sub work group to develop the purchase units for the specifications.

The network where requested has supported organisations on the national specialist palliative care gap analysis.

## National consortium to develop national guideline implementation plans

In February 2009 a consortium (the New Zealand Guidelines Group (lead contract holder), the regional cancer networks (with Midland as lead), the Royal New Zealand College of General Practitioners, the Melanoma Network (MELNET), the Health Sponsorship Council and the Cancer Society of New Zealand collaborated on a proposal for Guideline Implementation Plan Development and were successful as the preferred provider. The national guidelines involved are:

- Guidelines for the Management of Early Breast Cancer (published)

- Clinical Practice guidelines for the Management of Melanoma in Australia and New Zealand (published)

- Access and Referral (Suspected Cancer) Guidelines (published).

The Ministry of Health’s purpose in funding development of guideline implementation plans has been to disseminate and embed the guidelines throughout the sector.

Section 2: Progress against the Midland Cancer Network Annual Work Plan 2009/10 for this period

To note, whilst this section identifies specific activities to be undertaken, a focus on addressing inequalities is embedded across all of the network’s activities. Note: blue indicates the Midland Cancer Network reporting requirements for the National Cancer Control Programme Work Plan 2009-2010

1. Service Quality Improvement Priority – Improve treatment of lung cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for lung cancer Strategic Plan ref: 2.1 | Promote clinical governance through the establishment of multidisciplinary tumour stream work groups and work with them to undertake the output/activities below. Establish Midland Lung Cancer Work Group - Terms of reference developed - Prioritise recommendations - Develop protocols, oversee CQI initiatives |  | Achieved Midland Lung Cancer Work Group established with clinical chair terms of reference and work programme. |
| Lung cancer service/patient mapping work programme Strategic Plan ref: 2.1.2, 2.2 | Gather baseline information and identify existing waiting times from primary care referral to treatment for patients with suspected lung cancer. | Wait times from referral to first treatment for lung cancer patients (excludes inpatient and acute admissions) will be collected by DHB and by ethnicity for quarter 4 2009/10 - Report to Ministry quarter 4 | In progress Mapping and baseline information collected and presented to the Midland Lung Cancer Work Group. |
|  | Complete service and patient mapping lung cancer report with CQI and reducing inequalities recommendations |  | In progress Draft report out for consultation in quarter 3 |
| Implementation of lung cancer guidelines/framework and standards Strategic Plan ref:2.3, 2.3.2.3 | Stocktake and review of Suspected Cancer in Primary Care recommendations for lung cancer Explore implications and opportunities for lung cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |
| Regional quality improvement initiatives to improve lung cancer patient care Strategic Plan ref:2.4, 2.4.2.1 | Facilitate streamlining referral process to reduce the number of steps in the treatment pathway Sponsor two Lean Thinking training teams - GP referral to respiratory FSA - Referral to regional chest conference | Identify the percentage of suspected lung cancer patients that meet the 2 week standards from GP referral to FSA respiratory (elective services standard) - By quarter 2 (Dec 2009) | Achieved and ongoing - Refer to appendix for indicator report - Health Round Table training and support for the two regional training teams. Refer to appendix for summary of Lean findings and progress |
| Improve access to diagnostic services – PET-CT Strategic Plan ref: 2.4.1,2.4.2.2 | Agree clinical criteria for region Define and document decision making process Develop reporting and monitoring tool | Increased and equity of access to PET-CT - Bi-annual reporting of volumes by DHB and ethnicity | Achieved all actions, ongoing review and refinement is still required with new Ministry of Health CFA funding requirements (Dec09) Refer to appendix for PET-CT Indicator report |
| Promote development of MDM and improve continuity of care Strategic Plan ref:2.5 | Complete stocktake of current situation Develop MDM criteria and framework Improve MDM access within available resources | Identify the current percentage of lung cancer patients presented at multidisciplinary team meetings (regional chest conference) by DHB and by ethnicity - by quarter 2 (Dec 2009) | In progress Stocktake completed MDM project scope developed and will commence quarter 3. Refer to appendix for MDM Indicator report |
| Participate and support NCN primary lung cancer translational research project (that includes Lakes) Strategic Plan ref:1.5.3 | Within available resources provide support as required |  | Ongoing Midland cancer Network attended the hikoi ki Te Arawa in August 2009 in Rotorua |
| Develop regional lung cancer workforce framework and plan Strategic Plan ref:3.2, 2.7 | Identify current resources within each DHB that support developing cultural competency within the cancer workforce Identify gaps and opportunities within available resources |  | In progress Stocktake and consultation commenced, delayed to resignation of staff. |

2. Service Quality Improvement Priority – Improve treatment of bowel cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for bowel cancer Strategic Plan ref: 2.1 | Promote clinical governance through the establishment of multidisciplinary tumour stream work groups and work with them to undertake the output/activities below. Establish Midland Colorectal Cancer Work Group - Terms of reference developed - Prioritise recommendations - Develop protocols, oversee CQI initiatives | Improve wait times from referral to first treatment for lung cancer - Report to Ministry quarter 4 | Achieved Midland Colorectal Cancer Work Group established with clinical chair terms of reference and work programme. |
| Bowel cancer service/patient mapping work programme Strategic Plan ref: 2.1.2, 2.2 | Gather baseline information and identify existing waiting times from primary care referral to treatment for patients with bowel cancer | Baseline information by June 2010 | In progress Note unlikely to complete by June 2010 due to loss of personnel. |
|  | Complete service and patient mapping bowel cancer report with CQI and reducing inequalities recommendations |  |  |
| Implementation of bowel cancer guidelines/framework and standards Strategic Plan ref:2.3 | Stocktake and review of Suspected Cancer in Primary Care recommendations for lung cancer Explore implications and opportunities for lung cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |
| Regional quality improvement initiatives to improve bowel cancer patient care Strategic Plan ref:2.4.3 | Develop and undertake capacity and demand planning model with the aim to increase colonoscopy services |  | In progress Baseline information collection started |
| Promote development of MDM and improve continuity of care Strategic Plan ref:2.5 | Complete stocktake of current situation Develop MDM criteria and framework Improve MDM access within available resources | Identify the current percentage of bowel cancer patients presented at multidisciplinary team meetings by DHB and by ethnicity - by quarter 4 | In progress Stocktake completed MDM project scope developed and will commence quarter 3. |
| Develop regional bowel cancer workforce framework and plan Strategic Plan ref:3.2 | Identify current and future resources workforce requirements for bowel cancer |  | Minimal progress Completed national bowel cancer colonoscopy stocktake questionnaire |

3. Improve regional planning of Midland non-surgical cancer treatment services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Support achievement of national cancer health target – radiation and medical oncology Strategic Plan ref:3.1, 3.1.2 | Review and update the Midland NSCTS Plan (2004) Refresh data, review and update plan focusing on medical and radiation oncology services Continue to facilitate and support the MCN NSCT Work Group and associated initiatives. | Updated Midland NSCTS plan | In progress First draft radiotherapy plan 2010-2015 out for consultation |
|  | Review regional chemotherapy chair and nurse requirements for the future |  | In progress Project scope endorsed by Executive Group |

4. Improve regional planning of Midland palliative care services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote and develop regional palliative care planning and services Strategic Plan ref:3.5 | Review and update the Midland DHB palliative care plans taking a collaborative and regional approach | Midland palliative care plan | In progress Approach agreed with stakeholders, will commence quarter 3 |
| Best practice palliative care end of life programme Strategic Plan ref:2.4.5 | Continue to facilitate and support the MCN Palliative Care Work Group and associated initiatives. Continue to support implementation of LCP across Midland. Scope opportunities to implement the reflective data cycle tool. Continue to support implementation of the Midland palliative care education framework for generalist nurses and carers. Actively participate in the national development of the specialist palliative care service specifications, purchase units and reporting requirements. | Midland LCP implementation plan developed - Increase the number of Midland organisations that have implemented EoL LCP | In progress Progressing well Refer to appendix for LCP Indicator report Reflective data cycle principles agreed with Waikato network including input from National LCP Office. Midland Palliative Care Education Framework and Plan developed with all specialist stakeholders. Ongoing input in to the national service specifications. |

5. Service quality improvement – improve access to supportive care information and services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Develop and maintain a Midland supportive care service directory Strategic Plan ref:1.3.3 | Develop a MCN supportive care service directory Establish MCN Supportive Care Work Group - Chair appointed - Terms of reference agreed |  | Achieved Work Group established with chair and terms of reference In progress |
|  | Stocktake current cancer supportive care services within Midland. Publish Midland supportive care services directory |  |  |
| Implementation of best practice guidelines/framework and standards Strategic Plan ref:1.4.6 | Stocktake and review of Guidance for Improving Supportive and Rehabilitation for lung and bowel cancer Explore implications and opportunities for lung and bowel cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |

6. Service quality improvement – reduce inequalities, improve access and waiting times for breast cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Continue to support Midland Breast Work Group Strategic Plan ref:2.1.1 | MCN Breast Work Group meets and progresses service improvement initiatives related to the Midland Early Stage Breast Cancer report and improvement plan (2008) within available resources |  | Minimal progress No other progress due to loss of personnel |
| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| Improve wait times for Mâori breast cancer Strategic Plan ref:2.4.4.1 | Identify barriers and improve waiting times to critical stages of the breast cancer pathway for Mâori women. Re-audit waiting times against standards Identify barriers and opportunities to improve |  | In progress Audit of waiting times and chart review completed. Analysis will be reported quarter 3 |
| Strategic Plan ref:2.4.4.3 | Improve process flow to stereotactic biopsy Re-audit waiting times against standards | Audit actual wait times for stereotactic biopsy waiting times of 14 days by March 2010 | In progress Requested & received data for 6 month period. Analysis will occur quarter 3. |
| Promote and support implementation of the Early Stage Breast Cancer Guideline Strategic Plan ref:2.3.2 | When published disseminate to network stakeholders. Make guideline available on MCN website. Include availability in MCN quarterly newsletter. |  | Achieved |
| Support BSM to achieve national target Strategic Plan ref:2.4.4 | Support BSM action plan to increase Mâori and Pacific screening rates |  | Achieved and ongoing |

7. Service quality improvement – adolescent/young adult cancer services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Continue to support Midland AYA Cancer Services Work Group Strategic Plan ref:2.1.1 | Work group meets and works on service improvement initiatives relate to the Midland AYA OHS report and Improvement Plan (2008) within available resources. |  | In progress Midland AYA study day held November Developed AYACS booklet for Waikato oncology ward. Midland AYACS database developed. New AYACS logo developed. Infection Alert card reviewed and updated, with help of consumers. Letter to GP re service. |

8. Midland Cancer Network infrastructure development

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for major tumour and service work groups Strategic Plan ref:2.1.2 | Establish Midland Genitourinary Cancer Work Group - Terms of reference developed |  | In progress Chair appointed and draft terms of reference developed CNS appointed and orientating |
|  | Facilitate MCN research and audit day. Based on evaluation establish Midland Research and Audit Work Group - Terms of reference developed - Chair appointed Develop research and audit resource on website. |  | Achieved and ongoing |
| Build IS capacity for regional planning, audit, monitoring and evaluation Strategic Plan ref: 3.6 | MCN IS sector/market scan project completed. Explore opportunities to utilise the national Business Objects Intelligence Tool sitting on top of the Cancer Datamart (incorporates NZ Cancer Registry and other data collections). Develop a MCN database for regular audit and reporting requirements. |  | Achieved – completed market scan and report published and shared with CIO and MoH. Achieved - agreement and process for NZ regional cancer networks to have access NZ Cancer Registry data and other data. In progress – Somerset feasibility study to occur 2010-11 |
| Implement the MCN communications plan recommendations Strategic Plan ref:3.10 | MCN continues to develop and refine an operations framework that describes the functions and form of how the network will accomplish the strategic goals, objectives and service requirements. |  | Achieved |
|  | MCN actively participates in the National Mâori Cancer Conference and identifies opportunities for information sharing and service improvement. |  | Achieved Staff presented as well as attending including consumer representative |
|  | Quarterly Koha O Matauranga email newsletter with MCN including stakeholder contributions/updates disseminated to stakeholders. |  | Achieved and ongoing |
|  | Implement website password protected area. Develop website research and audit resource |  | Achieved |
| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| Jointly lead and facilitated annual national cancer control conference with other RCNs and MoH Strategic Plan ref:1.5.5 | Participate in developing conference themes, speakers. Assist with facilitation and administrative support as required with conference. |  | No progress |
| Disseminate and promote national and regional guidelines and pathways Strategic Plan ref:1.4 | Disseminated national guidelines as developed Actively participate in NZGG consortium agreement to develop national implementation plan for melanoma, breast and suspected cancer in primary care (note dependant on publication of guidelines) |  | Achieved and ongoing |
| Support Oranga Tane Mâori joint research proposal Strategic Plan ref:1.5.4 | Within available resources provide support as required for the three year research proposal. |  | In progress |

Appendix A – Lean Thinking Projects

- Project title:	Rotorua hospital receipt of referral from GP to first specialist assessment (FSA) for suspected lung cancer.

Purpose: The purpose of the project was to use Lean Thinking tools to review the process for receipt of referral to FSA at Rotorua Hospital for suspected lung cancer and improve the percentage of cases who meet a benchmark of 14 days.   Lakes baseline data (from Jan 07 to June 08) was 52%, the target for improvement was to reach 72%.

Achievements June to November 2009:

- 75% of patients are being seen within 14 days from receipt of referral to FSA.  The median time is 7 days and the range is 1 to 17 days.  The original target has been consistently met or exceeded.

- Standard email referral template developed and distributed via the GP Liaison at Rotorua Hospital.  The email template works well when used.

- Single point of entry for referrals has been implemented to the extent possible within the current resources of Rotorua Hospital outpatients department.

- Concept of joint clinic/FSA with nurse specialist and respiratory physician has been agreed and is currently implemented if a patient is travelling from outside Rotorua where all required tests and appointments are co-ordinated to one day.

- Project title: Streamlining the process of referral to the weekly regional Chest Conference (multidisciplinary meeting) and reducing delays in the lung cancer journey.

Purpose: To improve the process of referral to Chest Conference at Waikato Hospital so that all referrals have all relevant documentation available for decision making at the next meeting.  When documentation and/or imaging are not available this leads to an unnecessary 7 day delay in the patient journey.

Project objectives: Using lean thinking tools and methodologies:

- identify the issues and barriers for referral to the weekly regional Chest Conference at Waikato Hospital

- make recommendations and implement agreed improvements

- 100% referrals have all relevant documentation by December 2009.

Achievements June to November 2009:

Reducing delays

The charts below show the improvement with no information or films missing (categories 3 and 4) in the period October to December 2009.  This means that patient journeys were not delayed

Table Legend

- Category 1 – % patients discussed at conference where a decision was made, with all relevant films and information available

- Category 2 – % patients discussed at conference where a decision was made to do further investigations

- Category 3 - % patients taken to conference and not discussed due to lack of information

- Category 4 - % patients taken to conference and not discussed due to films not available

Key factors facilitating this improvement include:

- Improved understanding and service from Films on Loan

- Implementation of PACS at Bay of Plenty DHB in August and Waikato DHB in November

- Increased awareness of the impact of incomplete information

Chest Conference agendas

The decision by respiratory physicians to refer all people with lung cancer to Chest Conference led to increased referrals with subsequent pressure on time to discuss each patient at the meeting.  In August it was decided that those people needing a PET-CT would have this prior to Chest Conference.  Average numbers for agendas in Q2 have reduced from 21 in Q1 to 17.

Work continues to standardise the referral process.

- Indicator:  Improve timeliness of treatment for lung cancer (Draft)

Rationale

The Ministry of Health has signalled that lung cancer is a priority focus. These measures target improved and more timely access to assessment, diagnostic and treatment services and support the implementation of the New Zealand Cancer Control Strategy and New Zealand Health strategy priority of reducing the incidence and impact of cancer.

Reporting period

Six monthly in quarter 2 and quarter 4.  Timing of reporting should occur as follows:

- Quarter 2, should report on rates for lung cancer registrations for 12 months to 30 June of the previous financial year

- Quarter 4, should report on rates for lung cancer registrations for 12 months to 31 December of the previous year

| Indicator | Lung cancer (Draft) |
| --- | --- |
| Indicator 1.1: | The waiting time between GP referral and respiratory FSA should be 2 weeks (14 days) for all patients diagnosed with lung cancer or with symptoms suggestive of lung cancer |
| Deliverables: | Measure 1 The median waiting time (in days) between GP referral and respiratory FSA for patients diagnosed with lung cancer in a 12 month rolling period (moving every six months being reported). By: - Midland Cancer Network region - DHB (Bay of Plenty, Lakes, Waikato) - Ethnicity (Other and Māori) Measure 2 Percentage of patients that meet wait time standard of two weeks (14 days) between GP referral and respiratory FSA. By: - Midland Cancer Network region - DHB (Bay of Plenty, Lakes, Waikato) - Ethnicity (Other and Māori) Numerator: Total number of patients who had a waiting time less than or equal to 14 days Denominator: Total number of patients in sample |
| Data source | NZ Cancer Registry for information on patients diagnosed with lung cancer DHB information systems for referral and FSA dates. |
| Commentary: | For patients with a confirmed diagnosis of lung cancer only (as per New Zealand Cancer Registry). Currently it is not possible to define and identify patients with ‘suspected’ lung cancer. Referral source is from GPs only. Does not include other types of admissions/referrals (e.g. internal, emergency department, other physicians) Does not include patients who had a first specialist assessment with a general physician in hospitals where there is no respiratory physician or with a physician from another speciality (e.g. geriatrician) NHIs for lung cancer registrations from New Zealand Cancer Registry are cross matched with hospital information systems. Indicator report will always be six months behind due to timeliness/limitations of accessing New Zealand Cancer Registry information. |

Baseline information for this indicator

Source: Midland Cancer Network audit of 635 patients who had a hospital attendance for diagnosis or treatment of lung cancer during the period 1 January 2007 to 30 June 2008.

Measure 1:	Wait time between GP referral and respiratory FSA

| DHB/Region | Ethnicity | Median (days) |
| --- | --- | --- |
| Bay of Plenty | All | 22 |
|  | Māori | 29 |
|  | Other | 21 |
| Lakes | All | 14 |
|  | Māori | 18 |
|  | Other | 12 |
| Waikato | All | 14 |
|  | Māori | 20 |
|  | Other | 14 |
| Midland | All | 18 |
|  | Māori | 24 |
|  | Other | 17 |

Measure 2:	Number of patients who met two week (14 day) benchmark

| DHB/Region | Ethnicity | No. who met 14 day benchmark (%) |
| --- | --- | --- |
| Midland | All | 38 |
|  | Māori | 31 |
|  | Other | 41 |

Note:

Information available at regional level only

Quarter 2 2009/2010 Reporting

| DHB/Region | Ethnicity | Median (days) | No. who met 14 day benchmark (%) |
| --- | --- | --- | --- |
| Bay of Plenty | All |  |  |
|  | Māori |  |  |
|  | Other |  |  |
| Lakes | All | 17 | 40 |
|  | Māori | 14 | 50 |
|  | Other | 24 | 36 |
| Waikato | All | 13 | 56 |
|  | Māori | 14 | 33 |
|  | Other | 13 | 62 |
| Midland | All |  |  |
|  | Māori |  |  |
|  | Other |  |  |

Note:

Information for Bay of Plenty DHB could not supplied at this point in time and therefore Midland rates could not be calculated. This information will be provided in Quarter 4.

| Indicator: | Lung cancer (Draft) |
| --- | --- |
| Indicator 1.2: | 100% of patients with lung cancer are presented to Chest Conference (regional clinical multidisciplinary meeting for thoracic malignancy) |
| Deliverables: | The percentage of patients with a confirmed diagnosis of lung cancer patients in a 12 month rolling period which are presented to Chest Conference by: - Midland Cancer Network - DHB (Bay of Plenty, Lakes, Waikato) - ethnicity (Māori and Other) Numerator: Number of unique patients with lung cancer presented at Chest Conference Denominator: Number of lung cancer registrations for Midland Cancer Network DHBs in a 12 month rolling period |
| Data source | Waikato DHB Lung cancer database New Zealand Cancer Registry |
| Commentary: | Waikato lung cancer database is not up to date at this point in time. NHIs for lung cancer registrations from New Zealand Cancer Registry are cross matched with hospital information systems. Indicator report will always be six months behind due to timelines/limitations of accessing New Zealand Cancer Registry information |

Baseline information for this indicator

Source: Midland Cancer Network audit of 635 patients who had a hospital attendance for diagnosis or treatment of lung cancer during the period 1 January 2007 to 30 June 2008.

| DHB/Region | Ethnicity | No. of patients presented at Chest Conference (%) |
| --- | --- | --- |
| Bay of Plenty | All | 29 |
|  | Māori | 25 |
|  | Other | 29 |
| Lakes | All | 32 |
|  | Māori | 23 |
|  | Other | 36 |
| Waikato | All | 68 |
|  | Māori | 72 |
|  | Other | 67 |
| Midland | All | 45 |
|  | Māori | 45 |
|  | Other | 45 |
| Tairawhiti** | All | 69 |
|  | Māori | 83 |
|  | Other | 57 |

Note: Only 13 patients from Tairawhiti DHB were referred to Waikato DHB during the audit period.

Quarter 2 2009/2010 Reporting

| DHB/Region | Ethnicity | No. of patients presented at Chest Conference (%) |
| --- | --- | --- |
| Bay of Plenty | All | 40  |
|  | Māori | 34  |
|  | Other | 42  |
| Lakes | All | 61  |
|  | Māori | 67  |
|  | Other | 57  |
| Waikato | All | 62  |
|  | Māori | 69  |
|  | Other | 59  |
| Midland | All | 54  |
|  | Māori | 55  |
|  | Other | 53  |

- Indicator: PET-Scanning (Draft)

Rationale

PET-CT is an essential component to support clinical decision-making on the appropriate treatment for some patients with cancer. These measures target:

- improved access to PET scanning based on agreed clinical indications and for other indications as approved by the regional variance committee

- application of consistent practices and equitable access for PET scanning across the Midland Cancer Network region

- increased DHB spending on PET scanning including incorporation of the Ministry of Health funding boost to address past inequalities in PET scanning

Reporting period

To be reported in Quarters 2 and 4.

Quarter 2: should report PET volumes between 1 July and 31 December for current funding period

Quarter 4: should report PET volumes between 1 January and 30 June for current funding period

| Indicator | PET-CT (Draft) |
| --- | --- |
| Indicator: 2 | Number of PET-CT scans |
| Deliverables: | The number of PET-CT scans in line with agreed clinical indications and approved by variance committee (until a national indicator is determined). By: - Midland Cancer Network region - DHB (Bay of Plenty, Lakes, Waikato) |
| Data source | DHB PET-CT spreadsheet and communications with lead contact person from Midland Cancer Network DHBs |
| Commentary: | Projected PET volumes based on Ministry of Health’s modelling PET volumes by indication and estimated PET scans approved by variance committee (December 2009). Lakes DHB Planning and Funding allocates funding to its provider arm for “high cost procedures” includes PET-CT scanning and other procedures. Lakes DHB has no PET budget at this point in time. Ministry of Health PET boost funding for Tairawhiti DHB is split between between MidCentral (90%) and Waikato (10%) DHBs Variance procedures developed, however variance committee not yet established. |

Quarter 2 2009/2010 Reporting

|  | Actual PET Volumes (1/07/09 -31/12/2009) | 2008/09 PET Volumes | Projected PET volumes | 2009/10 PET Budget |
| --- | --- | --- | --- | --- |
| Bay of Plenty | 22 | 18 | 78 | 24 |
| Lakes | 2 | 3 | 36 | 0* |
| Waikato | 38 | 24 | 123 | 100 |
| Midland | 62 | 46 | 240 | 124 |
| Tairawhiti** | 0 | 1 | 2 | 0 |

Notes

Actual PET volumes for Lakes DHB are still provisional

* Lakes DHB Planning and Funding allocates funding to its provider arm for “high cost procedures” includes PET-CT scanning and other procedures. Lakes DHB has no PET budget at this point in time.

**Ministry of Health PET boost funding for Tairawhiti DHB is split between MidCentral (90%) and Waikato (10%) DHBs

    - Indicator:  Palliative Care (draft)

Rationale

The specialist palliative care service specification (draft, MOH 2008) requires the implementation of pathways for improving end of life care for people whose death is expected within days rather than weeks regardless of setting.  Midland Cancer Network organisations have chosen to implement the Liverpool care of the dying pathway (LCP) framework and tool.

Reporting period

To be reported in Quarters 2 and 4.  Timing of reporting should occur as follows:

- in Quarter 2, should report on implementation of LCP to 30 June

- in Quarter 4, should report on implementation of LCP to 31 December

| Indicator | Palliative care - End of Life (EoL) Liverpool Care Pathway (LCP) Draft |
| --- | --- |
| Indicator: | Increase the number of Midland eligible organisations that have implemented EoL LCP (expressed as a percentage) |
| Deliverables: | Measure 1 The percentage of target organisations or groups within Midland that have implemented LCP by: - DHB (Bay of Plenty, Lakes, Waikato) - All Midland organisations Numerator: Number of areas/providers identified as appropriate for LCP who have completed education to enable the use of LCP Denominator: Total number of areas/providers identified as appropriate to implement LCP (expressed as a percentage) Measure 2 The percentage change between the current and previous reporting periods. |
| Data source: | Each DHB lead organisation will have a district palliative care LCP implementation plan and the lead LCP facilitator will record information on the areas targeted for implementation of LCP and the areas where education has been completed. A regional spreadsheet is in development. |
| Commentary: | - In large hospitals (Waikato, Tauranga and Rotorua) wards/units are counted individually - Smaller community hospitals, residential care facilities, hospice inpatient units and GP practices will be counted individually - District nurse teams are counted individually by area. This indicator relates to the implementation of LCP only, not to the sustainability of LCP. |

Measure 2 – Percentage change between reporting periods

Bay of Plenty – no measure avail for July 09

Taupo/Turangi increased by 30%

Rotorua implementation has not yet commenced

Waikato increased by 7%

DHB PET-CT spreadsheet and communications with lead contact person from DHBs

Letter of 17 December 2009 to DHB CEOs from Ministry of Health

Letter of 17 December 2009 to DHB CEOs from Ministry of Health

Waikato DHB Cancer PET scanning process and communications with lead contact person from Bay of Plenty and Lakes DHBs