Section 2: quarter 4 progress against the Midland Cancer Network Annual Work Plan 2009/10

To note, whilst this section identifies specific activities to be undertaken, a focus on addressing inequalities is embedded across all of the network’s activities. Note: blue indicates the Midland Cancer Network reporting requirements for the National Cancer Control Programme Work Plan 2009-2010

1. Service Quality Improvement Priority – Improve treatment of lung cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for lung cancer Strategic Plan ref: 2.1 | Promote clinical governance through the establishment of multidisciplinary tumour stream work groups and work with them to undertake the output/activities below. Establish Midland Lung Cancer Work Group - Terms of reference developed - Prioritise recommendations - Develop protocols, oversee CQI initiatives |  | Achieved Midland Lung Cancer Work Group established with clinical chair terms of reference and work programme. |
| Lung cancer service/patient mapping work programme Strategic Plan ref: 2.1.2, 2.2 | Gather baseline information and identify existing waiting times from primary care referral to treatment for patients with suspected lung cancer. | Wait times from referral to first treatment for lung cancer patients (excludes inpatient and acute admissions) will be collected by DHB and by ethnicity for quarter 4 2009/10 - Report to Ministry quarter 4 | Achieved and ongoing development Refer to annual report for KPI report Mapping and baseline information collected and presented to the Midland Lung Cancer Work Group. |
|  | Complete service and patient mapping lung cancer report with CQI and reducing inequalities recommendations |  | Achieved and ongoing Report developed and made available to Midland lung cancer work group |
| Implementation of lung cancer guidelines/framework and standards Strategic Plan ref:2.3, 2.3.2.3 | Stocktake and review of Suspected Cancer in Primary Care recommendations for lung cancer Explore implications and opportunities for lung cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |
| Regional quality improvement initiatives to improve lung cancer patient care Strategic Plan ref:2.4, 2.4.2.1 | Facilitate streamlining referral process to reduce the number of steps in the treatment pathway Sponsor two Lean Thinking training teams - GP referral to respiratory FSA - Referral to regional chest conference | Identify the percentage of suspected lung cancer patients that meet the 2 week standards from GP referral to FSA respiratory (elective services standard) - By quarter 2 (Dec 2009) | Achieved and ongoing Refer to annual report for KPI report Health Round Table training and support for the two regional training teams |
| Improve access to diagnostic services – PET-CT Strategic Plan ref: 2.4.1,2.4.2.2 | Agree clinical criteria for region Define and document decision making process Develop reporting and monitoring tool | Increased and equity of access to PET-CT - Bi-annual reporting of volumes by DHB and ethnicity | Achieved all actions, ongoing review and refinement is still required with new Ministry of Health CFA funding requirements (Dec09) Refer to annual report for PET-CT Indicator report |
| Promote development of MDM and improve continuity of care Strategic Plan ref:2.5 | Complete stocktake of current situation Develop MDM criteria and framework Improve MDM access within available resources | Identify the current percentage of lung cancer patients presented at multidisciplinary team meetings (regional chest conference) by DHB and by ethnicity - by quarter 2 (Dec 2009) | In progress Stocktake completed MDM project scope developed Refer to annual report for MDM Indicator |
| Participate and support NCN primary lung cancer translational research project (that includes Lakes) Strategic Plan ref:1.5.3 | Within available resources provide support as required |  | Ongoing Midland cancer Network attended the hikoi ki Te Arawa in August 2009 in Rotorua |
| Develop regional lung cancer workforce framework and plan Strategic Plan ref:3.2, 2.7 | Identify current resources within each DHB that support developing cultural competency within the cancer workforce Identify gaps and opportunities within available resources |  | In progress Stocktake and consultation commenced, delayed to resignation of staff. |

2. Service Quality Improvement Priority – Improve treatment of bowel cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for bowel cancer Strategic Plan ref: 2.1 | Promote clinical governance through the establishment of multidisciplinary tumour stream work groups and work with them to undertake the output/activities below. Establish Midland Colorectal Cancer Work Group - Terms of reference developed - Prioritise recommendations - Develop protocols, oversee CQI initiatives | Improve wait times from referral to first treatment for lung cancer - Report to Ministry quarter 4 | Achieved Midland Colorectal Cancer Work Group established with clinical chair terms of reference and work programme. |
| Bowel cancer service/patient mapping work programme Strategic Plan ref: 2.1.2, 2.2 | Gather baseline information and identify existing waiting times from primary care referral to treatment for patients with bowel cancer | Baseline information by June 2010 | In progress Refer to annual report for baseline indicator report |
|  | Complete service and patient mapping bowel cancer report with CQI and reducing inequalities recommendations |  | In progress |
| Implementation of bowel cancer guidelines/framework and standards Strategic Plan ref:2.3 | Stocktake and review of Suspected Cancer in Primary Care recommendations for lung cancer Explore implications and opportunities for lung cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |
| Regional quality improvement initiatives to improve bowel cancer patient care Strategic Plan ref:2.4.3 | Develop and undertake capacity and demand planning model with the aim to increase colonoscopy services |  | In progress Elective service review completed |
| Promote development of MDM and improve continuity of care Strategic Plan ref:2.5 | Complete stocktake of current situation Develop MDM criteria and framework Improve MDM access within available resources | Identify the current percentage of bowel cancer patients presented at multidisciplinary team meetings by DHB and by ethnicity - by quarter 4 | In progress Stocktake completed MDM project scope developed |
| Develop regional bowel cancer workforce framework and plan Strategic Plan ref:3.2 | Identify current and future resources workforce requirements for bowel cancer |  | Minimal progress Completed national bowel cancer colonoscopy stocktake questionnaire Refer to annual report for baseline indicator report |

3. Improve regional planning of Midland non-surgical cancer treatment services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Support achievement of national cancer health target – radiation and medical oncology Strategic Plan ref:3.1, 3.1.2 | Review and update the Midland NSCTS Plan (2004) Refresh data, review and update plan focusing on medical and radiation oncology services Continue to facilitate and support the MCN NSCT Work Group and associated initiatives. | Updated Midland NSCTS plan | In progress Final draft radiotherapy plan 2010-2015 out for consultation |
|  | Review regional chemotherapy chair and nurse requirements for the future |  | In progress Project scope endorsed by Executive Group |

4. Improve regional planning of Midland palliative care services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote and develop regional palliative care planning and services Strategic Plan ref:3.5 | Review and update the Midland DHB palliative care plans taking a collaborative and regional approach | Midland palliative care plan | In progress Completed consultation with Lakes and BOP, paediatrics and regional Maori hui |
| Best practice palliative care end of life programme Strategic Plan ref:2.4.5 | Continue to facilitate and support the MCN Palliative Care Work Group and associated initiatives. Continue to support implementation of LCP across Midland. Scope opportunities to implement the reflective data cycle tool. Continue to support implementation of the Midland palliative care education framework for generalist nurses and carers. Actively participate in the national development of the specialist palliative care service specifications, purchase units and reporting requirements. | Midland LCP implementation plan developed - Increase the number of Midland organisations that have implemented EoL LCP | In progress and ongoing Progressing well Refer to annual report for LCP Indicator report Reflective data cycle principles agreed with Waikato network including input from National LCP Office. Midland Palliative Care Education Framework and Plan developed with all specialist stakeholders. Ongoing input in to the national service specifications. |

5. Service quality improvement – improve access to supportive care information and services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Develop and maintain a Midland supportive care service directory Strategic Plan ref:1.3.3 | Develop a MCN supportive care service directory Establish MCN Supportive Care Work Group - Chair appointed - Terms of reference agreed |  | Achieved Work Group established with chair and terms of reference In progress |
|  | Stocktake current cancer supportive care services within Midland. Publish Midland supportive care services directory |  |  |
| Implementation of best practice guidelines/framework and standards Strategic Plan ref:1.4.6 | Stocktake and review of Guidance for Improving Supportive and Rehabilitation for lung and bowel cancer Explore implications and opportunities for lung and bowel cancer within available resources |  | Minimal to no progress Actively participating in the NZGG Guideline Implementation Plan Project for Suspected Cancer in Primary Care and other guidelines. No other progress due to loss of personnel |

6. Service quality improvement – reduce inequalities, improve access and waiting times for breast cancer

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Continue to support Midland Breast Work Group Strategic Plan ref:2.1.1 | MCN Breast Work Group meets and progresses service improvement initiatives related to the Midland Early Stage Breast Cancer report and improvement plan (2008) within available resources |  | Minimal progress No other progress due to loss of personnel |
| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| Improve wait times for Mâori breast cancer Strategic Plan ref:2.4.4.1 | Identify barriers and improve waiting times to critical stages of the breast cancer pathway for Mâori women. Re-audit waiting times against standards Identify barriers and opportunities to improve |  | In progress Audit of waiting times and chart review completed. Finalising report on findings for Midland Breast cancer Work Group |
| Strategic Plan ref:2.4.4.3 | Improve process flow to stereotactic biopsy Re-audit waiting times against standards | Audit actual wait times for stereotactic biopsy waiting times of 14 days by March 2010 | Achieved Refer to annual report for indicator report |
| Promote and support implementation of the Early Stage Breast Cancer Guideline Strategic Plan ref:2.3.2 | When published disseminate to network stakeholders. Make guideline available on MCN website. Include availability in MCN quarterly newsletter. |  | Achieved |
| Support BSM to achieve national target Strategic Plan ref:2.4.4 | Support BSM action plan to increase Mâori and Pacific screening rates |  | Achieved and ongoing |

7. Service quality improvement – adolescent/young adult cancer services

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Continue to support Midland AYA Cancer Services Work Group Strategic Plan ref:2.1.1 | Work group meets and works on service improvement initiatives relate to the Midland AYA OHS report and Improvement Plan (2008) within available resources. |  | In progress Midland AYA study day held November Developed AYACS booklet for Waikato oncology ward. Midland AYACS database developed. New AYACS logo developed. Infection Alert card reviewed and updated, with help of consumers. Letter to GP re service. |

8. Midland Cancer Network infrastructure development

| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| --- | --- | --- | --- |
| Promote clinical governance for major tumour and service work groups Strategic Plan ref:2.1.2 | Establish Midland Genitourinary Cancer Work Group - Terms of reference developed |  | In progress Chair appointed and draft terms of reference developed CNS appointed and orientating |
|  | Facilitate MCN research and audit day. Based on evaluation establish Midland Research and Audit Work Group - Terms of reference developed - Chair appointed Develop research and audit resource on website. |  | Achieved and ongoing |
| Build IS capacity for regional planning, audit, monitoring and evaluation Strategic Plan ref: 3.6 | MCN IS sector/market scan project completed. Explore opportunities to utilise the national Business Objects Intelligence Tool sitting on top of the Cancer Datamart (incorporates NZ Cancer Registry and other data collections). Develop a MCN database for regular audit and reporting requirements. |  | Achieved – completed market scan and report published and shared with CIO and MoH. Achieved - agreement and process for NZ regional cancer networks to have access NZ Cancer Registry data and other data. In progress – Somerset feasibility study to occur 2010-11 |
| Implement the MCN communications plan recommendations Strategic Plan ref:3.10 | MCN continues to develop and refine an operations framework that describes the functions and form of how the network will accomplish the strategic goals, objectives and service requirements. |  | Achieved |
|  | MCN actively participates in the National Mâori Cancer Conference and identifies opportunities for information sharing and service improvement. |  | Achieved Staff presented as well as attending including consumer representative |
|  | Quarterly Koha O Matauranga email newsletter with MCN including stakeholder contributions/updates disseminated to stakeholders. |  | Achieved and ongoing |
|  | Implement website password protected area. Develop website research and audit resource |  | Achieved |
| Key Focus Area | Specific actions | Milestones / Indicator | Progress |
| Jointly lead and facilitated annual national cancer control conference with other RCNs and MoH Strategic Plan ref:1.5.5 | Participate in developing conference themes, speakers. Assist with facilitation and administrative support as required with conference. |  | Decision with Ministry of Health not to proceed 2009-10 |
| Disseminate and promote national and regional guidelines and pathways Strategic Plan ref:1.4 | Disseminated national guidelines as developed Actively participate in NZGG consortium agreement to develop national implementation plan for melanoma, breast and suspected cancer in primary care (note dependant on publication of guidelines) |  | Achieved and ongoing |
| Support Oranga Tane Mâori joint research proposal Strategic Plan ref:1.5.4 | Within available resources provide support as required for the three year research proposal. |  | In progress |