Midland Cancer Network 2011-12 quarter 1 report

1 July – 30 September 2011

| Service Area: Cancer Control Initial discussions have occurred so as to ensure integration of reporting for Midland Cancer Network activities via the MRCSP Programme office. Current priority initiatives include: - Developing the Midland Radiation Oncology Services Plan - Developing the Midland Medical Oncology Services Plan - Undertake a feasibility review of Waikato to be the potential provider of adult cancer treatment services for Tairawhiti DHB - Improving lung cancer services - Improving bowel cancer services - Developing the Midland DHBs Palliative Care Service Plans and quality initiatives - Implement infrastructure requirements to improve access to MDMs - Host the National Lung Cancer Work Group developments. As this is an established network, resourcing is already in place to manage the work plan with developed project management processes. | Green |
| --- | --- |

Improved cancer control through increased regional collaboration to:

- reduce the incidence and impact of cancer

- reduce inequalities with respect to cancer

- improve the experience and outcomes for people with cancer.

The Midland Cancer Network strategic directions are to:

- share knowledge and information to enable informed decision making

- facilitate regional service quality improvement leading to better, sooner, more convenient services

- support innovation and infrastructure development to reduce inequalities and build capacity and capability.

This report summarises progress on priority areas.  Refer to the Midland Cancer Network 2011-12 Work Plan for detail on other aspects of the work programme.  The work plan aligns with the Midland Cancer Network Strategic Plan 2009-2014 and the National Cancer Work Programme priorities.

The following provides detail on progress to date.

Clinical Director: 				Dr Charles de Groot

Manager: 					Jan Smith

| Summary of key actions 2011/12 | ..to deliver these milestone outputs in 2011/12 | Status at 30 September 2011 | Percent completed | Planned completion date | Progress comments & Supporting details |
| --- | --- | --- | --- | --- | --- |
| - Implement first stages of the Midland Radiation Oncology Services Plan 2010-2020 | - Continue development and implementation of the Midland Radiation Oncology Services Plan - Regular audit of RCC work flow - Enhance information systems wherever possible to assist with audit, service planning/improvement and reporting. | In progress | 20% | ongoing | Regional Cancer Centre plan developed to support Waikato business case for linac – completed. Meeting with Ministry of Health to implement national radiotherapy modelling tool 21-9-11. MOH presented benchmarking data to MCN Executive 30-8-11. Completed Tairawhiti analysis. |
| - Support Tairawhiti DHB tertiary cancer review findings | - Complete the Waikato and Tairawhiti Cancer Collaborative Project | In progress | 90% | 14 Oct 2011 | Service requirements and consultation completed. First draft report reviewed by Steering Group 16-9-11. |
| - Complete development of Midland Medical Oncology Plan/oncology pharmacy model of care & implement within available funding | - Incorporate findings from the national model of care initiative - Assist organisations with audit and reporting of developing National Medical Oncology and Haematology Indicators - Upgrade/implement Aesculapius chemotherapy system - Develop and implement Midland Chemotherapy Nursing Certification Project - Continue to work on development of a Midland Oncology Pharmacy Model of Care | In progress | 20% | ongoing | Midland Service Plan development in progress. Upgrade/implement Aesculapius chemotherapy system completed. Medical oncology indicator reporting occurring. Haematology indicator reporting some aspects started. Midland Chemotherapy Nursing Certification Draft Framework out for consultation. |
| - Implement recommendations of lung cancer elective service review | - Midland Lung Cancer Work Group - Standardise diagnostic work up for suspected lung cancer - Develop regional clinical triaging criteria/guidelines and process for FSA and bronchoscope - Improve Chest Conference MDM facilities/processes to improve regional access - Enhance regional Chest Conference lung cancer database - Improve access to EBUS - Improve access to CT and CT FNA - Complete Rotorua Cough, Cough, Cough initiative | In progress | 25% | ongoing | Work group scheduled for November. Stocktake of current service provision against national standards in progress. Indicator reporting for 1/1/10-31/12/10 cancer registrations completed and sent to MoH 30-9-11. Early trends demonstrating improvement. Mini Lung Cancer Conference planning for November. Inaugural Endobronchial Ultrasound Service (EBUS) commenced at Waikato and available for regional DHBs. Audit commenced on staging of Rotorua 2010 lung cancer cases. |
| - Host National Lung Cancer Work Group developments, inc lung cancer service framework and standards for MD teams | - Support implementation of National Lung Cancer Standards - Stocktake of priority areas and develop recommended action plan - Complete development of National Lung Cancer Service Framework that underpins the standards - Refining the national lung cancer indicators - Lung cancer minimum data set defined. | In progress | 20% | 30 June 2012 | National Lung Cancer Standards published and distributed. Stocktake questionnaire developed and distributed to NZ networks to complete. Stakeholder database developed. |
| - Implement recommendations of bowel cancer elective service review | - Midland Bowel Cancer Work Group - Improve colonoscopy waiting list management - Agree criteria for regional colonoscopy prioritisation - Develop colonoscopy capacity and demand management - Implement regional colorectal cancer patient diary (utilise Waikato) - Explore regional opportunities to replace obsolete/implement endoscopy reporting system - Develop regional and local MDMs and ability to capture decisions and relevant data for reporting - Lakes implement Ministry GRS | In progress | 20% | ongoing | Work group and MoH/Lakes GRS meeting on 20/7/11. Each DHB has local work group Indicator reporting for 1/1/10-31/12/10 cancer registrations completed and sent to MoH 30-9-11. Joint MCN/RIS Endoscopy Reporting System Workshop 19-9-11 (incl. Taranaki & Tairawhiti). Systems implement to capture MDM indicator data for all DHBs – noted improvement since 2010-11. |
| - Implement infrastructure requirements to improve access to MDMs | - Confirm MDM infrastructure requirements - Purchase/implement MDM equipment / databases - Support operational change management - If approved participate in NZ RCN MDM coordinator project (SCN lead) | In progress | 25% | ongoing | MDM facility stocktake completed, AV equipment requirements identified. Agreed process to purchase with Midland COOs. NZ RCN’s, MOH met with National Health IT Board to present reasons why MDM & connectivity development is a priority |
| - Implement first stages of Midland Palliative Care Services Plan | - Facilitate implementation - Continue to facilitate implementation of Liverpool Care Pathway - Continue to implement Midland Palliative Care Education Framework programme - Scope feasibility of Regional Integrated PalCare System | In progress | 25% | ongoing | Midland Palliative Care forum held 5 July with MOH/PCNZ Lakes consultation and documentation completed. BOP 90% completed. Waikato consultation in progress. Midland workshop on the National Draft Resource and Capability Framework 20-9. Midland hospices have commenced implementation of Pal_Care. |

Other Midland key achievements/progress of note for the quarter:

- Midland Cancer Network effective 1 August 2011 will be part of HealthShare Ltd.  Transition to HealthShare is in progress.

- Midland Research and Audit Sharing Day was well attended on 19th July 2011 with Chair Professor Ross Lawrenson.

- The network facilitated and sponsored a regional sexual intimacy workshop for cancer CNS and radiation therapists on 3rd August.  This was in response to the CCNZ Cancer Voices of Experience opportunity for areas of improvement.

- Inaugural Midland Cancer Network Māori Advisory Group meeting held 13th September, this included Taranaki and Tairawhiti representatives.

- Midland Breast Cancer Work Group meeting 16th September.  Key new developments include:

  - “Exercise and wellbeing during treatment for breast cancer at Waikato” booklet for women – will explore adopting regionally

  - Waikato nurse led telephone assessment clinic: adjuvant endocrine therapy – new service – will explore adopting regionally

  - Waikato follow-up guidance for patients treated for early stage breast cancer – will explore adopting regionally

- The Midland Prostate Cancer Research project is progressing well.  Preliminary findings presented at the Research and Audit Sharing Day.

- First Midland Cancer Network Monitoring and Evaluation Report published.  This reference report presents a set of cancer performance indicators along the cancer continuum by DHB.

- The network in partnership with the Waikato/Bay of Plenty Cancer Society and Aroha Mai in Rotorua held the first Consumer and Carer Forum where people who had gone through treatment and supporting family/whānau could come together to share their experiences.

- In response to the Waikato Regional Cancer Centre urgent request for dedicated social work resourcing, the new Group Manager Allied Health has responded with a dedicated 0.2 fte that will commence 14 October.

- The Genitourinary CNS and Radiation Oncologist completed a Bladder Cancer Audit to ascertain the time taken from diagnosis of invasive bladder cancer to cystectomy as definitive treatment.  Refer to website for further detail.  Other audits to drive service improvement are planned.