| Project Details |  |  |
| --- | --- | --- |
| Project Title |  | Midland Medical Oncology Service Plan 2011-2021 |
| Project Sponsor |  | Jan Smith, Manager, Midland Cancer Network |
| Project Manager |  | Mo Neville, Project Manager Midland Cancer Network |
| Document Control |  |  |
| Plan compiled by | Mo Neville |  |
| Associated documents | Midland Cancer Network Strategic Plan 2009-2014 |  |
|  | Midland Cancer Network 2011-12 Work Plan |  |
|  | Non-Surgical Cancer Treatment Services Plan for the Midland Region (2004) |  |
|  | Midland Region Non-Surgical Cancer Treatment Service; Progress Report 2005; Implementation Plan 2005-2010 (2005) |  |
|  | Cranleigh Health Models of Care report – due publication in October 2011 |  |
|  | Waikato Radiotherapy service plan 2010 |  |
|  | Midlands DHB service plan 2011/2012 |  |
|  | Medical Oncology Nursing Workforce Forecast Modelling (MOH) |  |
| Definitions |  |  |
| Background to project | Cancer affects one in three people in the New Zealand population. Medical oncology co-ordinates the aspect of cancer care related to systemic therapy, including cytotoxic chemotherapy, targeted hormonal and molecular therapy or immunotherapy, and aspects of supportive care and is often used in conjunction with other forms of cancer treatment such as radiation therapy and / or surgery. Access to flexible treatment options are a necessary part of the journey for many cancer patients with up to 85% of all cancer patients benefiting from chemotherapy as part of their treatment plan. Medical oncology plays an important part in both curative and palliative (symptom relief in incurable cancer) treatment for cancer It is now recognised that the increase in oncology treatment rates is greater than the increase in cancer incidence. Available data from New Zealand cancer centres indicates variable but consistent ongoing growth in medical oncology activities at approximately 9% annually This continuing growth in medical oncology activities is believed to be due to: - increasing use of adjuvant chemotherapy (e.g. for breast and colon cancer) - increasing use of combined chemotherapy and radiotherapy (e.g. for cervical, and head and neck cancers) - the development of effective treatments of cancers that were previously poorly responsive to chemotherapy (e.g. secondary colorectal cancer and potentially non-small cell lung cancer) - increasing cancer incidence and prevalence rates, and rising expectations of patients - management of common malignancies with multiple courses of therapy, as more effective palliative care is being developed - an increasing number of patients who previously were thought to be unsuitable for treatments (e.g. because of age) - The development of treatments with fewer side effects. Matched against this is an increasing difficulty in recruiting trained medical oncologists. There is a need to develop new, innovative but clinically effective work practices. |  |
| Project Linkages | - New Zealand Cancer Control Strategy (2003): - Goal 3, objective 1, action 44: Review of Non-Surgical Cancer treatment Plan - Provision of optimal treatment for those with cancer. Provision of diagnostic and treatment services within defined specifications Goal 5 action 91: Improved capacity and capability of the cancer nursing workforce Cranleigh Health Models of Care report - implementation of recommendations |  |
| Project Goal | The purpose of this plan is to outline the strategic direction and operational requirements for medical oncology within the Midland Cancer Network over the next ten years |  |
| Project Objectives | - Identify key issues affecting the current medical oncology services at each of the DHB’s - Outline the key strategic considerations for improving the quality and safety of patient care over the next ten years - Identify and prioritise the key actions required at short / medium and long term at a regional and DHB level - Identify the costs to implement the plan |  |
| Deliverables | - Midland Cancer Network Non-Surgical Cancer Treatment Work Group - Draft service plan for discussion by Midland Cancer Network Executive Group - Draft service plan for discussion / agreement by Midland DHB CEO’s - Final service plan for publication and implementation |  |
| Benefits of project | - Assists individual DHBs within the Midland region through developing effective and efficient processes and systems to enable timely access to chemotherapy within limited resources - Improved access and services for chemotherapy patients across the region - Supports best practice for patients and their families across the region |  |
| Coverage (inclusion) | Chemotherapy and associated therapies administered to adults as inpatients / outpatients across Bay of Plenty, Lakes and Waikato DHBs |  |
| Coverage (exclusions) | Chemotherapy for paediatrics Resolution of day to day operational issues |  |

| Stakeholders |  |
| --- | --- |
| Key stakeholders | Bay of Plenty, DHBs - Rosemary Davies – CNM Oncology Outpatients - Chemotherapy nurses - Medical oncologists - Richard North - Clinical nurse managers (or equivalent) - Service managers – Neil McKelvie - Director of nursing - ? Julie Robinson - Chief operating officers Lakes - Elaine Warner, CNM chemotherapy - Chemotherapy nurses - Medical oncologists - Clinical nurse managers (or equivalent) - Service managers – Jane Chittenden - Director of nursing - ? Gary Lees - Chief operating officers Waikato - Kate Yeo – Nurse Manager, Oncology - Shona Hoggart – CNM oncology outpatients - Gabby Reynolds - CNM oncology inpatients - Medical oncologists – Michael Jameson, Ian Kennedy, Marion Kuper - Fraser Tumai – Nurse Educator - Wendy Thomas, CNM Clinical Trials - Service managers – Sharon Donnell - Jacqui Mitchell - Thames - Chemotherapy nurses - Director of nursing – Sue Hayward - Chief operating officers – Mark Spittle / Jan Adams Midland Cancer Network Executive Group Midland Cancer Network Non-Surgical Cancer Treatment Work Group |
| Other stakeholders | - People receiving chemotherapy treatment and their family/whānau - all ethnic groups - Oncology pharmacists - Baxter pharmaceutical compounding - Other allied health professionals - NGO / Maori providers - Primary care staff |
| Communication Plan | Initial meetings with key stakeholder representatives prior to development of project scope following publication of Cranleigh ‘new models of care’ report Progress reports to Midland Non Surgical Cancer Treatment Work Group and Midland Cancer Network Executive Group |
| Key Constraints | Availability of accurate data to inform current and future demand |

| Project Approach and Management |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project approach | Work with key stakeholders to gather information about current service delivery and future planning utilising a mix of face to face interviews, questionnaires and workshops Identify current activity / demand Confirm current volumes and predict future volumes for chemotherapy Literature review of best practice related to chemotherapy including chemotherapy workforce frameworks, and capacity tools Link project initiatives with national Cranleigh work currently underway Horizon scanning for future service models and technology developments |  |  |  |
| Project start date | June 2011 | Project completion date | November 2012 |  |
| Financial summary | The Midland Cancer Network will support the project lead and associated operational costs. DHB staff will be supported by their organisation to participate in this project as part of business as usual. |  |  |  |
| Milestones |  |  |  | Date |
| Project scope signed off |  |  |  | July 2011 |
| Literature review inc Cranleigh report |  |  |  | August 2011 |
| Information gathering through interviews and questionnaires |  |  |  | September 2011 |
| Draft version 1 |  |  |  | December 2011 |
| Final report |  |  |  | November 2012 |
| Implementation |  |  |  | ongoing |

| RISKS AND RISK MANAGEMENT |  |  |  |
| --- | --- | --- | --- |
| Risks | Probability (low, med, high) | Impact (low, med, high) | Risk management strategy |
| Work pressures experienced by stakeholders compromise their engagement | M | M | Maintain excellent communication and follow-up missed due dates |
| Data availability – known issues given manual collection in Waikato | M | H | Work closely with Midland Cancer Network analyst and clinical nurse managers / local IS staff to resolve issues |
| Stakeholder expectations exceed available resources | M | L | Executive leadership and support with clear communication about scope of this project |
| National recommendations are different to local expectation | L | H | - Monitoring through regular communication with Cranleigh |

| AUTHORISATION |  |  |  |
| --- | --- | --- | --- |
| Project Sponsor |  | Date |  |

Bibliography

Barber J. 2004. Non-Surgical Cancer Treatment Services Plan for the Midland Region. Tauranga: Midland District Health Boards.

Cancer Services Collaborative Improvement Partnership. 20… Modernising chemotherapy services – a practical guide to redesign.

Royal College of Physicians. 2007. Making your chemotherapy service more patient-friendly. Retrieved from http://www.rcr.ac.uk/docs/oncology/pdf/PatientChemo_web.pdf

Scanlan L, & Hewitt J. 2005. Midland Region Non-Surgical Cancer Treatment Service; Progress Report 2005; Implementation Plan 2005-2010. Hamilton: Midland District Health Boards.