# ADULT PALLIATIVE CARE SERVICES

# WORKPLAN 2012/2013

Draft – v1

Note this work plan is based on the Recommendations of the report and identifies key areas discussed at this meeting.  Further discussion on other recommendations will be raised at future meetings

| Service plan ref no. | Service Plan recommendation | 2012/13 Actions | Success measure | Project lead |
| --- | --- | --- | --- | --- |
| 1. 29. | Continue to develop the specialist medical palliative care visiting service for Rotorua Hospital, fully integrated with the Rotorua community specialist PC service. Also: Specialist services to strengthen relationships and support to local acute hospital services (also refer to #1). | Promote availability of visiting specialist in hospital for patient consults, education, patient reviews Establish inservice sessions for palliative medicine specialist with hospital nurses and junior doctors Promote ability to access 24/7 medical phone advice from Waikato palliative medicine specialists. Link with Primary Care organisations to arrange education opportunities e.g. case reviews, formal education sessions | Reminder of visiting specialist attendance sent each month to primary practices and Rotorua Hospital (Hospice to action) Number of consults, education sessions /participants Number of calls for support Number of education sessions/participants | Denise Aitken Support: Lara Hoskins and Rotorua Hospice staff (PHOs) |
| 2. | Regularly monitor utilisation and demand for palliative care medical specialist input to palliative care and education in Rotorua and Taupo with the lead provider, and anticipate required changes to meet local population need. | Capture and record information on visiting specialist services - Number of consults/home visits - Education sessions / number of participants Regular monitoring utilisation & demand with lead provider and Rotorua and Taupo Hospitals | Process in place to record information Needs are reviewed at least annually. | Sharron Black (Rotorua) Suzie Kuper (Taupo) |
| 4. | PHOs to develop and implement sustainable solutions which ensure all palliative people have access to a general practitioner. Relates to specific issues in Taupo for out of hours access. | Discuss with MHN, develop plan | - Out of hour’s access issues resolved. - Community aware of access arrangements | Midlands Health Network Support Vanessa Russell Suzie Kuper |
| 7. | Implement the Hospice NZ programme ‘Fundamentals of Palliative Care’. | Continue to deliver training. Focus on residential care with ability for home care agencies and others to attend. | Number/percentage of residential care facilities with staff having completed training Number of participants | Sharron Black (Rotorua) Suzie Kuper (Taupo) |
| 8. | Implement cultural competency education for health professionals in specialist palliative care services where required. | Possibility of using Mauriora online programme. To be discussed/confirmed | Number of hospice staff having completed cultural competency training | Sharron Black (Rotorua) Suzie Kuper (Taupo) Support: Lauren James |
| 9. | Develop and implement topic specific education sessions for palliative care health professionals. | Rotorua establish and promote access to monthly Waikato Palliative Care Grand Round via video link Investigate/enable hospice, residential care staff and others e.g. Maori Health provider services) to access hospital clinical education sessions e.g. renal, respiratory, cardiac. | Access/link established Number of participants Range of programmes and number of attendees from NGOs etc. | ? Lara & MCN team 7 Denise Denise Aitken |
| 13. | Initiate a project to scope access to grief and loss/bereavement/counselling services in Lakes particularly for those people who are not referred to specialist palliative care services. | To be discussed at October meeting with Te Rananga o Ngati Pikiao Trust representative. |  | ? |
| 14. | Lake Taupo Hospice transition model of care from shared care with district nursing to hospice community nursing (implementation 1 July 2012). | Monitor changes to ensure continuity of care for palliative people in the community. Establish KPIs to measure and monitor service change. Undertake evaluation. | - Report on KPIs to Planning and Funding - Share evaluation & lessons learned | Suzie Kuper |
| 20. | Develop a Lakes palliative care service directory. | Plan and ‘publish’ service directory | Service directory completed | Sharon Hardaker |
| 21. | Review and strengthen website content of the DHB, hospices, Māori health providers, PHOs and other relevant NGOs. | - Review current website content - Discuss opportunity for improvements in information relating to palliative care and palliative care services. Will also link with service directory (above) | Improvements implemented | ? with Hospices, DHB communications staff and other organisations |
| 31. | Develop and document service level agreements between specialist palliative care services and others. | Need to identify the services where these are required What do other Hospices/DHBs have? | Service level agreements/MOU implemented between identified services | Vanessa |