NZ Breast Cancer Working Group – Stakeholder Update

December 2012

Membership

Ian Campbell (Chair), Anne Allan-Moetaua, Grant Broadhurst, Libby Burgess, Raewyn Calvert, Mary Christie, Brigit Dijkstra, Mark Elwood, Alison Foster, Marli Gregory, Claire Hardie, Gavin Harris, Barbara Hochstein, Marion Kuper, Cheryl MacDonald, Glenys Mitchell, Kiri Peita, Garth Poole, David Porter, Glenys Round, Jeremy Sharr and Meredith Simcock. Loryn Scanlan (project manager).

National Breast Cancer Work Programme 2012/13

- National breast cancer service standards

- National breast cancer patient pathway

- Consider a data set to monitor standards and clinical outcomes

Activity July – December 2012

The breast cancer working group has met twice in face to face meetings with its third meeting to take place in February 2013. Members are working on drafting the breast cancer standards document. Three subgroups have been set up to work on systemic therapy, high risk and supportive care sections / subsections between now and February 2013. The working group is also seeking additional input from the national genetic health service and supportive care experts.

Timeline for completing work

| Activity | When |
| --- | --- |
| 1st draft of standards and 1st meeting | 26 September 2012 |
| 2nd draft of standards and 2nd meeting | 14 November 2012 |
| 3rd draft of standards and 3rd meeting | 25 February 2013 |
| Stakeholder consultation on standards | 1 April to 14 May 2013 |
| 4th meeting working group (to consider feedback) | May 2013 |
| Breast cancer standards finalised | 30 June 2013 |

Consultation

The working group will be seeking feedback on its draft standard.  A six week consultation period is planned for April and May 2013. You will be contacted again in the New Year about the opportunity to review and provide feedback on the draft breast cancer standards.

You can view more information on the National Breast Cancer Working Group on the Midland Cancer Network website www.midlandcancernetwork.org.nz

Information on the other seven tumour stream standards is available through the Ministry of Health website www.moh.govt.nz or from the Northern Cancer Network website www.northerncancernetwork.org.nz.

If you have any questions or for up to date information on the breast cancer standards projects please contact Loryn Scanlan (project manager) on 07 859 9154 or 021 341 917 or loryn.scanlan@waikatodhb.health.nz.