| Project Details |  |
| --- | --- |
| Project Title | Midland Colonoscopy Service Improvement Project 2015 |
| Sub-Project 3 | Midland Demand and Capacity Modelling Framework |
| Project Sponsor | Dr Humphrey Pullon, Clinical Director Midland Cancer Network |
| Programme Lead | Jan Smith, Manager Midland Cancer Network |
| Project Manager | Lu-ana Ngatai, Service Improvement and Project Manager |
| Clinical Lead | TBC |

| Document Control |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan compiled by |  | Lu-ana Ngatai |  |  |  |  |  |  |  |  |  |
| Associated documents |  | DHB Strategic Plans DHB Regional Plans DHB Annual Plans |  |  |  |  |  |  |  |  |  |
| Inter-related projects |  | Elective Services Initiative projects |  |  |  |  |  |  |  |  |  |
| Definitions |  |  |  |  |  |  |  |  |  |  |  |
| Background to project |  | Some DHBs recognise to manage demand (current and future) may require a regional approach. There is no known regional demand and capacity modelling in place for Midland DHBs to use, and collectively Midland does not have a picture of current and future requirements. The regional work is expected to help the DHBs to be better prepared to meet colonoscopy rates at 2015/16 indicator levels, and to prepare for colonoscopy demands generated by the possible introduction of a national bowel screening programme. |  |  |  |  |  |  |  |  |  |
| Project Goal |  | To develop a regional demand and capacity modelling framework for Midland DHBs to utilise for their colonoscopy services. |  |  |  |  |  |  |  |  |  |
| Project Objectives |  | To develop a regional demand and capacity modelling framework. To consider options for a sustainable process for managing colonoscopy patients, using the framework. To develop information tools utilising regional qlickview (business intelligence and data visualisation software) to assist with future planning. |  |  |  |  |  |  |  |  |  |
| Deliverables |  | A regional demand and capacity modelling framework. |  |  |  |  |  |  |  |  |  |
| Benefits of project |  | Regional view of current and future demand, capacity and gaps in volumes, workforce, facilities, equipment. |  |  |  |  |  |  |  |  |  |
| Coverage (incl) |  | Bay of Plenty, Lakes, Waikato and Tairawhiti DHB regions. |  |  |  |  |  |  |  |  |  |
| Coverage (excl) |  | Taranaki DHB. Patients treated in private. |  |  |  |  |  |  |  |  |  |
| Stakeholders |  |  |  |  |  |  |  |  |  |  |  |
| Expert Work Group |  | Bay of Plenty DHB Dr Abid Saadeddin – Clinical Director Neil McKelvie – Service Manager Mesa Premlall - Clinical Nurse Manager Lakes DHB Dr Charlie Richardson – Clinical Director Greg Vandergoot – Service Manager Anne Marie Murphy - Colorectal Nurse Specialist Chrissy Rees – ACNM Perioperative area Tairawhiti DHB Dr Peter Stiven – Clinical Director Lynsey Bartlett – Acting Chief Operating Officer Dawn Tucker - Theatre Manager Waikato DHB Dr Graeme Dickson – Clinical Director Amanda Wright – Assistant Group Manager, Medicine Andrea Coxhead – Business Unit Manager, Medicine and Endoscopy TBC – Clinical Nurse Manager Decision Support staff from each of the Midland DHBs Midland Cancer Network project staff |  |  |  |  |  |  |  |  |  |
| Other stakeholders |  | Chief Operating Officers from each DHB General Managers Planning and Funding from each of the Midland DHBs |  |  |  |  |  |  |  |  |  |
| Communication Plan |  | Internal DHB communication will be the responsibility of management and clinical directors of each DHB. Regional and project communications including minutes of meetings, memorandums, reports will be provided by the Midland Cancer Network. |  |  |  |  |  |  |  |  |  |
| Key Constraints |  | The project will struggle to meet the timeframes set if the information required to build the models and scenarios is not readily available. |  |  |  |  |  |  |  |  |  |
| Project Approach and Management |  |  |  |  |  |  |  |  |  |  |  |
| Project approach | Across the country other DHB and cancer networks have been working on local demand and capacity modelling frameworks. The Midland cancer network will review these models; resource Qlikview(the Midland developed regional resource for capacity planning), and work with the DHBs to develop a regional model based on the information they request. |  |  |  |  |  |  |  |  |  |  |
| Project start date | 30 January 2015 |  |  |  | Project completion date |  |  |  |  | 30 June 2015 |  |
| Financial summary | Midland Cancer Network will provide project support and facilitation to DHBs as required. Healthshare Ltd analysts have agreed to provide modelling framework support to the Midland project |  |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  |  |  |  |  |  |  | Date |
| - Modelling scenarios to be used for demand and capacity tabled. - Parameters, data source, timeframes discussed. |  |  |  |  |  |  |  |  |  |  | 12 April 2015 |
| - Draft modelling frameworks completed. - Modelling scenario information analysed and presented to workgroup. |  |  |  |  |  |  |  |  |  |  | 23 April 2015 |
| - Revised modelling frameworks completed and presented to work group. |  |  |  |  |  |  |  |  |  |  | 28 May 2015 |
| - Regional Demand and Capacity Frameworks agreed by working group. |  |  |  |  |  |  |  |  |  |  | 30 June 2015 |
| - Options for a sustainable process for managing colonoscopy patients agreed. |  |  |  |  |  |  |  |  |  |  | 30 June 2015 |
| - Feedback on the use of qlikview as a regional tool. |  |  |  |  |  |  |  |  |  |  | 30 June 2015 |
| - Final report to the Ministry of Health. |  |  |  |  |  |  |  |  |  |  | 3 July 2015 |
| RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| Risks |  |  |  | Probability (low, med, high) |  | Impact (low, med, high) |  | Risk management strategy |  |  |  |
| Information not readily available |  |  |  | high |  | high |  | Prioritise data already captured and build on this |  |  |  |
| Stakeholders expectation create modelling tool parameters that are too big and complex |  |  |  | med |  | high |  | Prioritise the demand and capacity data components and business rules |  |  |  |
| Timeframes to tight to achieve milestones. |  |  |  | med |  | high |  | Increase resource into project to assist in meeting timeframes. Note – this will need ongoing review and development |  |  |  |
| AUTHORISATION |  |  |  |  |  |  |  |  |  |  |  |
| Project Sponsor |  |  |  |  |  |  | Date |  |  |  |  |

| WORK PLAN Date |  |
| --- | --- |
| Discuss demand and capacity modelling options with Healthshare analysts and other DHBs, NEQIP team. | 25 March 2015 |
| Discuss modelling scenarios and parameters to be considered at working group meeting | 12 March 2015 |
| Table modelling scenarios as options that could be developed. | 12 March 2015 |
| Milestones 1 & 2 completed. | 12 March 2015 |
| Research and gather data and relevant information for agreed modelling scenarios. | 10 April 2015 |
| Prepare modelling scenarios. | 13 April 2015 |
| Quality checks of modelling scenario work. | 17 April 2015 |
| Present modelling framework drafts to working group for feedback and revision. | 23 April 2015 |
| Milestone 3 & 4 completed. | 23 April 2015 |
| Make any agreed alterations to modelling and draft regional options for considerations proposal. | 15 May 2015 |
| Regional clinical directors and managers agree preferred demand and capacity frameworks. | 28 May 2015 |
| Milestone 5 & 6 completed. | 28 May 2015 |
| Regional demand and capacity modelling framework endorsed by Midland working group Working group consider options for regional delivery of colonoscopy based on information in regional modelling framework. | 30 June 2015 |
| Milestone 7 completed. |  |
| Regional sustainable plan for managing surveillance patient’s agreed. Feedback on the use of qlikview as a regional tool. | 30 June 2015 |
| Milestone 7 completed. | 30 June 2015 |
| Draft report submitted to the Ministry. | 3July 2015 |
| Final report submitted to the Ministry. | 17 July 2015 |
| Milestone 8 completed. | July 2015 |