| Project Details |  |
| --- | --- |
| Project Title | Midland Colonoscopy Service Improvement Project 2015 |
| Sub Project 1 | Increasing Utilisation and Implementation of GRS Quality Improvement tools |
| Project Sponsor | Dr Humphrey Pullon, Clinical Director, Midland Cancer Network |
| Programme Lead | Jan Smith, Manager Midland Cancer Network |
| Project Manager | Alison Hearn, Project and Service Improvement Manager, Midland Cancer Network |
| NZGRS Expertise | Jenni Masters, Sector Implementation Director, National Endoscopy Quality Improvement Programme (NEQIP) |
| Clinical Lead |  |

| Document Control |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan compiled by |  | Alison Hearn |  |  |  |  |  |  |  |  |  |
| Associated documents |  | New Zealand Global Rating Scale – National overview Report Sapere Project – future development of a national governance structure |  |  |  |  |  |  |  |  |  |
| Inter-related projects |  | Regional wait list management project. Regional nurse consent process project. Regional implementation of provation (business support) project. |  |  |  |  |  |  |  |  |  |
| Definitions |  |  |  |  |  |  |  |  |  |  |  |
| Background to project |  | A review of publicly funded endoscopy services was undertaken and the DHB Endoscopy Services Summary Report was published in July 2011. The review identified a number of issues and it was determined by the sector that a co-ordinated multi-pronged approach was required to ‘optimise clinical performance, endoscopy unit performance and enhance training and assessment’. The Global Rating Scale (GRS), a patient centred endoscopy quality improvement tool, was agreed as the way forward, with 21 patient centred items measured. The NEQIP rollout of the GRS to all DHBs commenced early 2013 after demonstrations, pilots and evaluation. Lakes DHB was a demonstration site. The GRS tool is a self-assessment tool undertaken by the individual unit. It provides a set of standards that enables endoscopy units to report how well they provide patient centred care. Units self-assess and load their scores quarterly into the GRS census database. Scoring is from A to D with A as the highest. NEQIP analyse the scoring and assist units whose implementation is in the C and D ratings. An endoscopy reporting system (ERS), ProVation, is also an essential part of achieving the GRS standards as it assists units to achieve an A status which will lead to accreditation. The Sapere group have been commissioned to do a report to guide the development of an appropriate governance structure for GRS and in February 2015 commenced consultation with stakeholders. The national report to the Ministry Bowel Cancer Team will help inform the structure of a regional governance group for Midland. |  |  |  |  |  |  |  |  |  |
| Project Goal |  | Individual DHBs are prepared to be able to move towards an accreditation process |  |  |  |  |  |  |  |  |  |
| Project Objectives |  | 1. Complete a stocktake of where each DHB is at 2. Work with Sapere, NEQIP and the MOH to consider options for a regional governance structure for Midland 3. Increase the completion of GRS items per DHB |  |  |  |  |  |  |  |  |  |
| Deliverables |  | 1. Stocktake completed 2. Regional governance structures for the GRS work confirmed 3. Regional supported quality improvement tools implemented where required |  |  |  |  |  |  |  |  |  |
| Benefits of project |  | Regional sustainable clinical governance Regional consistency of improved quality of services |  |  |  |  |  |  |  |  |  |
| Coverage (inclusion) |  | Includes Bay of Plenty, Lakes, Waikato and Tairawhiti DHB |  |  |  |  |  |  |  |  |  |
| Coverage (exclusions) |  | Taranaki DHB. |  |  |  |  |  |  |  |  |  |
| Stakeholders |  |  |  |  |  |  |  |  |  |  |  |
| Expert Work Group |  | Bay of Plenty DHB Dr Abid Saadeddin – Clinical Director Neil McKelvie – Service Manager Mesha Premlall - Clinical Nurse Manager, endoscopy Lakes DHB Dr Charlie Richardson – Clinical Director Greg Vandergoot – Service Manager Chrissy Rees – Clinical Nurse Manager, endoscopy Anne Marie Murphy – Colo-rectal nurse specialist Tairawhiti DHB Dr Peter Stiven Lynsey Bartlett – Acting Chief Operating Officer Te Pare Meihana, Clinical Nurse Manager Waikato DHB Dr Graeme Dickson – Clinical Director Amanda Wright – Service Manager Helen Goldsmith – Clinical Nurse Manager, endoscopy Amanda Dee Souza – Registered Nurse, Endoscopy Decision Support staff from each of the Midland DHBs NEQIP Team Jenni Masters, Sector Implementation Director Nicola Wilson, Programme Manager David Theobald, Clinical Director Midland Cancer Network project staff |  |  |  |  |  |  |  |  |  |
| Other stakeholders |  | Endoscopy personnel Chief Operating Officers across the region. Ministry of Health Bowel Cancer team NEQIP team |  |  |  |  |  |  |  |  |  |
| Communication Plan |  | - Governance of the project will be through the Midland Cancer Network Executive group - Internal DHB communication as and when required will be the responsibility of management and clinical directors of each DHB |  |  |  |  |  |  |  |  |  |
| Key Constraints |  | Short time frame to reach full implementation |  |  |  |  |  |  |  |  |  |
| Project Approach and Management |  |  |  |  |  |  |  |  |  |  |  |
| Project approach | DHB Progress: Lakes - has completed the required items and is waiting on progressing ERS ProVation to be able to move to accreditation. BOP - has dedicated staff and has completed many of the items. Waikato - has had difficulty finding dedicated resource so will benefit most from this project in terms of assistance towards accreditation, building on what has already been achieved by other DHBs Tairawhiti - are working towards completion of items but at this stage we do not know their status The project team will undertake to work with all endoscopy unit managers to support DHBs with assistance in policy development and to implement and/or refine the current GRS policies by: - working closely with Lakes hospital to utilise their learnings from the GRS pilot - utilise the GRS database and the Knowledge Management System (KMS) to develop operational policies for the DHBs that require them - work alongside the NEQIP/MOH/Sapere team to assist their plans for accreditation and towards a regional governance model |  |  |  |  |  |  |  |  |  |  |
| Project start date | 30 January 2015 |  |  |  | Project completion date |  |  |  |  | 30 June 2015 |  |
| Financial summary | Midland Cancer Network will provide project support and facilitation to DHBs as required to the DHBs who will be leading the work. |  |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  |  |  |  |  |  |  | Date |
| - Complete stocktake of each unit progress to GRS accreditation - Agree the regional/local quality improvement initiative tools the DHBs wish to work on collectively. |  |  |  |  |  |  |  |  |  |  | March 2015 |
| 2. Finalise the tools for the regional quality improvement initiatives. |  |  |  |  |  |  |  |  |  |  | April 2015 |
| 3. Review progress of implementation to date Establish framework of regional governance structure |  |  |  |  |  |  |  |  |  |  | May 2015 |
| 4. Review implementation, lessons learnt and achievements made in improving quality initiatives for the region. |  |  |  |  |  |  |  |  |  |  | June 2015 |
| 5. Regional governance structure agreed |  |  |  |  |  |  |  |  |  |  | June 2015 |
| 6 Final report to the Ministry |  |  |  |  |  |  |  |  |  |  | July 2015 |
| RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| Risks |  |  |  | Probability (low, med, high) |  | Impact (low, med, high) |  | Risk management strategy |  |  |  |
| Sapere report on governance options not available within our project timeframe |  |  |  | med |  | med |  | Midland Cancer Network to work with Sapere and Ministry of Health Bowel Cancer Team, to get current information relating to trends and issues |  |  |  |
| Lack of available DHB resource to assist with project implementation |  |  |  | med |  | high |  | - Midland Cancer Network to assist DHBs (where able) with implementation of processes. |  |  |  |
| AUTHORISATION |  |  |  |  |  |  |  |  |  |  |  |
| Project Sponsor |  |  |  |  |  |  | Date |  |  |  |  |

| Work plan | Due |
| --- | --- |
| Contact individual personnel in the DHBs and NEQIP, and visit to introduce the project and seek their feedback on their priorities and align work done to date | 3 March 2105 |
| Collate information on all DHBs in terms of their issues/priorities/progress with GRS, to present at the meeting | 11 March 2015 |
| Confirm which regional GRS initiatives the region needs collective work on to make quality improvements Agree the level of individual unit needs and agree if the DHBs want to utilise those already developed or to develop local policies | 12 March 2015 |
| Milestone 1 and 2 completed. | March 2015 |
| Utilising KMS research the required operational policies and procedures | 7 April 2015 |
| Prepare draft quality improvement documents for the Clinical Group |  |
| Send out draft documents for comment | 15 April 2015 |
| Review draft documents such as the feedback notice, operational policy documents. | 23 April 2015 |
| Agree final tools and support implementation of the agreed tools | 28 April 2015 |
| Milestone 3 completed. | April 2015. |
| Attend NEQIP regional forum | 5 May 2015 |
| Review progress and implementation of improvement initiatives. | 28 May 2015 |
| Review progress of implementation to date Review findings from Sapere work to date on a national governance group for GRS and discuss with group the adaptions required for a regional group Complete a draft framework for governance structure | 28 May 2015 |
| Milestone 3 completed. | June 2015 |
| Meet with endoscopy user groups and NEQIP to seek feedback on implementation and lessons learned and successes achieved Work with NEQIP to review findings from Sapere research and advise User Group. Finalise structure for regional governance group | 30 June 2015 |
| Milestone 4 and 5 completed. | June 2015. |
| Final draft report to the Ministry. | 3 July 2015 |
| Final report to the Ministry. | 17 July 2015 |
| Milestone 6 completed |  |