|  | Project Details |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project Title | Midland Colonoscopy Service Improvement Project 2015 |  |  |  |  |  |  |  |  |  |
|  | Sub-project 2 | Workforce – Endoscopy Nurse Consenting Process. |  |  |  |  |  |  |  |  |  |
|  | Project Sponsor | Humphrey Pullon – Clinical Director Midland Cancer Network. |  |  |  |  |  |  |  |  |  |
|  | Programme Lead | Jan Smith, Manager Midland Cancer Network. |  |  |  |  |  |  |  |  |  |
|  | Project Manager | Lydia Rickard, Project and Service Improvement Manager. |  |  |  |  |  |  |  |  |  |
|  | Clinical Lead |  |  |  |  |  |  |  |  |  |  |
|  | Document Control |  |  |  |  |  |  |  |  |  |  |
|  | Plan compiled by | Lydia Rickard |  |  |  |  |  |  |  |  |  |
|  | Associated documents | - HDC Code of Health and Disability Services Consumers' Rights Regulation 1996. - Health and Disability Services (Code) Standards NZS 8134.1:2008. - Nursing Council of New Zealand Competencies for Registered Nurses. - Medical Council of New Zealand: Statements - Standards for Doctors. |  |  |  |  |  |  |  |  |  |
|  | Inter-related projects | Midland Colonoscopy Service Improvement Project 2015. |  |  |  |  |  |  |  |  |  |
|  | Definitions |  |  |  |  |  |  |  |  |  |  |
|  | Background to project | Counties Manukau DHB introduced endoscopy nurse consenting process approximately three years ago. At CMDHB, the final consent for the procedure is done by the endoscopist. A pictorial pre consent patient information flipchart that covered the risks associated with colonoscopy as well as a learning module for endoscopy nurse consenting was developed. The content in the flipchart was approved by local endoscopists. If there are any additional risks not on the flipchart, the endoscopist is to discuss with the patient prior to the procedure. Bay of Plenty DHB has initiated the pathway for nurse led consenting and has developed consultation documents to support the process. |  |  |  |  |  |  |  |  |  |
|  | Project Goal | Midland DHB implementation of a colonoscopy nurse consenting process. |  |  |  |  |  |  |  |  |  |
|  | Project Objectives | Develop nurse consenting process for colonoscopy patients. |  |  |  |  |  |  |  |  |  |
|  | Deliverables | Midland DHBs colonoscopy nurse consenting process established. |  |  |  |  |  |  |  |  |  |
|  | Benefits of project | - Supports expanding scope of practice for registered nurses working in endoscopy units - Supports increased capacity by one more colonoscopy procedure per list. |  |  |  |  |  |  |  |  |  |
|  | Coverage (inclusion) | Bay of Plenty, Lakes, Tairawhiti and Waikato DHBs providing publicly funded endoscopy services. |  |  |  |  |  |  |  |  |  |
|  | Exclusions | - Private patients - Publicly funded patients undergoing colonoscopy in private facilities. |  |  |  |  |  |  |  |  |  |
|  | Stakeholders |  |  |  |  |  |  |  |  |  |  |
|  | Expert Work Group | Regional Colonoscopy Working Group Sub-Group (Nurse Consenting Process) Bay of Plenty Mesha Premlall, Clinical Nurse Manager Lakes Ann-Maree Murphy, Colorectal Nurse Specialist Chrissy Rees, ACNM, Perioperative Area Waikato Helen Goldsmith, Charge Nurse Manager Amanda DeSouza, Registered Nurse Endoscopy Tairawhiti Dawn Tucker, Theatre Manager |  |  |  |  |  |  |  |  |  |
|  | Other stakeholders | - Directors of Nursing each Midland DHB - Chief Medical Officers and clinical directors at each Midland DHB - Midland COOs - Nurse educators at each Midland DHB - Quality and risk teams at each Midland DHB - Endoscopy unit nursing staff at each Midland DHB |  |  |  |  |  |  |  |  |  |
|  | Communication Plan | - Regional and project communications including minutes of meetings, memorandums, reports will be provided by the Midland Cancer Network - Internal DHB communication as and when required will be the responsibility of Clinical Nurse Managers. |  |  |  |  |  |  |  |  |  |
|  | Key Constraints | Short timeframe for project completion. |  |  |  |  |  |  |  |  |  |
|  | Project Approach and Management |  |  |  |  |  |  |  |  |  |  |
|  | Project approach | - This is a regional project led by the clinical nurse managers from each of the four Midland DHBs (excludes Taranaki DHB). - A collaborative approach is proposed to determine how the roll out of the Endoscopy Nurse Consent process will occur, and what the regionally agreed parameters will be around the scope of practice. - MCN Project Mangers will work with the DHBs to develop relevant documents necessary to support the implementation of the nurse consenting process. The documents should provide guidance and be able to be adapted to each DHB local requirements if necessary. |  |  |  |  |  |  |  |  |  |
|  | Project start date | 1 February 2015 |  |  | Project completion date |  |  |  |  | 30 June 2015 |  |
|  | Financial summary | This is a regional service improvement initiative that is supported by MCN who will support the DHB clinical nurse managers. |  |  |  |  |  |  |  |  |  |
|  | Milestones |  |  |  |  |  |  |  |  | Date |  |
|  | - Review and agree a regional roll out of a Midland endoscopy nurse consenting initiative. - Current status of consenting process at each DHB confirmed. |  |  |  |  |  |  |  |  | 12 March 2015 |  |
|  | - Each clinical team to develop an agreed local process for implementation. |  |  |  |  |  |  |  |  | 23 April 2015 |  |
|  | - Draft documents developed for consenting process to be signed off |  |  |  |  |  |  |  |  | 23 April 2015 |  |
|  | - Implementation of the nurse endoscopy consenting process commences |  |  |  |  |  |  |  |  | 28 May 2015 |  |
|  | - Complete project evaluation |  |  |  |  |  |  |  |  | 30 June 2015 |  |
|  | - Final report to Ministry of Health. |  |  |  |  |  |  |  |  | 3 July 2015 |  |
|  | RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |
|  | Risks |  |  | Probability (low, med, high) |  | Impact (low, med, high) |  | Risk management strategy |  |  |  |
|  | Lack of clinical / management buy-in to the roll out of the endoscopy nurse consenting initiative. |  |  | med |  | high |  | Ensure all clinical teams are on board with the agreed roll-out of the endoscopy nurse consenting project. |  |  |  |
|  | Delay in process for approving DHB policy/procedures. |  |  | med |  | high |  | - Ensure policy coordinators/quality and risk teams are aware of project. |  |  |  |
|  | AUTHORISATION |  |  |  |  |  |  |  |  |  |  |
|  | Project Sponsor |  |  |  |  |  | Date |  |  |  |  |
| Work plan |  |  |  |  |  |  |  |  |  |  | Date |
| - Email each DHB Service Manager to seek basic background information on nurse consenting at respective DHBs. |  |  |  |  |  |  |  |  |  |  | 25 February 2015 |
| - Request informed consent policies/procedures/guidelines from each DHB and other associated documents. |  |  |  |  |  |  |  |  |  |  | 25 February 2015 |
| - Potential issues with progressing nurse consent process identified. |  |  |  |  |  |  |  |  |  |  | 2 March 2015 |
| - Review and agree a proposed regional roll-out of the endoscopy nurse consenting initiative. |  |  |  |  |  |  |  |  |  |  | 12 March 2015 |
| Regional meeting #1 - Provide initial background information gathered from each DHB and agree with work group how a regional roll-out within the region can occur. - Stocktake of current consenting practices across the region reviewed. |  |  |  |  |  |  |  |  |  |  | 12 March 2015 |
| Milestone 1 & 2 completed. |  |  |  |  |  |  |  |  |  |  | 12 March 2015 |
| - Plan developed to address any issues that may cause delays in progressing the nurse consent process. |  |  |  |  |  |  |  |  |  |  | 23 March 2015 |
| - Identify regional documents required and develop for consultation. |  |  |  |  |  |  |  |  |  |  | 13 April 2015 |
| - Agreement on the criteria for nurses to apply to undertake nurse consent training. |  |  |  |  |  |  |  |  |  |  | 13 April 2015 |
| Regional meeting #2 - Update on the endoscopy nursing consenting initiative, highlighting any issues to be resolved, constraints associated with the implementation process and successes to date - Draft regional documents for endoscopy nurse consenting initiative submitted to the regional meeting for discussion and feedback. |  |  |  |  |  |  |  |  |  |  | 23 April 2015 |
| Milestone 2 & 3 completed. |  |  |  |  |  |  |  |  |  |  | 23 April 2015 |
| - Advise each DHB when nurse endoscopy consenting process pilot is ready to commence implementation. |  |  |  |  |  |  |  |  |  |  | 28 April 2015 |
| - Training of nurses completed. |  |  |  |  |  |  |  |  |  |  | 18 May 2015 |
| - Implementation of pilot nurse endoscopy consenting process commenced. |  |  |  |  |  |  |  |  |  |  | 25 May 2015 |
| Regional meeting #3 - Final regional documents and process for endoscopy nurse consenting initiative for sign off by work group. |  |  |  |  |  |  |  |  |  |  | 28 May 2015 |
| Milestones 4 completed |  |  |  |  |  |  |  |  |  |  | May 2015 |
| - Review of the outcomes of new process completed and provided to working group. |  |  |  |  |  |  |  |  |  |  | 30 June 2015 |
| - Draft report submitted to the Ministry. |  |  |  |  |  |  |  |  |  |  | 3 July 2015 |
| - Final report submitted to the Ministry. |  |  |  |  |  |  |  |  |  |  | 17 July 2015 |
| Milestone 5 & 6 completed. |  |  |  |  |  |  |  |  |  |  | 17 July 2015 |