| Project Details |  |
| --- | --- |
| Project Title | Midland Colonoscopy Service Improvement Project 2015 |
| Sub-Project 1 | Implementation of ProVation |
| Project Sponsor | Dr Humphrey Pullon, Clinical Director, Midland Cancer Network |
| Programme Lead | Jan Smith, Manager, Midland Cancer Network |
| Project Manager | Lu-ana Ngatai, Project and Service Improvement Manager |
| Clinical Lead |  |

| Document Control |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan compiled by | Lu-ana Ngatai |  |  |  |  |  |  |  |  |  |
| Associated documents | - Midland IS Executive Brief for ERS 2011/12. While prioritised on the Midland e-space work programme, was below the affordability threshold. - Taranaki DHB approval to implement ProVation Feb. 2102. Midland tender exception approved Feb. 2012. - A case for a regional approach for the purchase and implementation of a Midland DHB’s electronic endoscopy reporting system (MCN 9/9/2013). - Midland COOs decision April 2014 agreed regionally that Waikato would complete a local Waikato solution for implementation of ProVation, and Bay of Plenty, Lakes and Tairawhiti a phased approach to ProVation and utilise Taranaki platform as the regional platform. - Midland high-level design/architecture in preparation for Taranaki Upgrade (pre-business case work) 3/2/2014. |  |  |  |  |  |  |  |  |  |
| Inter-related projects | - Midland IS e-space work programme. - Waikato DHB implementation of ProVation. |  |  |  |  |  |  |  |  |  |
| Definitions |  |  |  |  |  |  |  |  |  |  |
| Background to project | ERS is an essential requirement for a modern endoscopy service to improve patient outcomes. ProVation is the preferred national IS system. There is national endorsement for a ProVation to support NEQIP. ProVation will support DHBs to achieve site accreditation for possible roll out of a national bowel screening programme. Refer to Midland associated documents above that provide additional background. |  |  |  |  |  |  |  |  |  |
| Project Goal | - To provide support to ensure ProVation implementation has commenced in all Midland DHBs by 30 June 2015. - To ensure Healthshare Limited IS and Taranaki IS upgrade to the ProVation platform is completed in preparation for DHB implementation. |  |  |  |  |  |  |  |  |  |
| Project Objectives | - ProVation implementation pathway for DHBs clearly agreed. - To support DHBs in development of operating policy and procedures. - Regional process agreed to manage upgrades and maintenance of ProVation. - Shared learnings from the installation and implementation of ProVation. |  |  |  |  |  |  |  |  |  |
| Deliverables | Implementation commenced of ProVation across the Midland region. |  |  |  |  |  |  |  |  |  |
| Benefits of project | - Essential tool for endoscopy services. - Supports safe patient care. - Tool to assist DHBs to achieve accreditation with ERS. |  |  |  |  |  |  |  |  |  |
| Coverage (inclusion) | - Includes Bay of Plenty, Lakes and Tairawhiti DHB. |  |  |  |  |  |  |  |  |  |
| Coverage (exclusions) | - Waikato DHB (already in process of implementing ProVation). Taranaki DHB. |  |  |  |  |  |  |  |  |  |
| Stakeholders |  |  |  |  |  |  |  |  |  |  |
| Expert Work Group | Bay of Plenty DHB Neil McKelvie – Service Manager Owen Wilson – Chief Information Officer Lakes DHB Greg Vandergoot – Service Manager Dale Oliff – Chief Operating Officer Alex Wheatley – Chief Information Officer Tairawhiti DHB Lynsey Bartlett – Acting Chief Operating Officer Ian Diamond – Information Systems Manager Waikato DHB Jolene Williamson – Waikato ProVation Project Manager John Lares – onsite ProVation consultant from the USA Healthshare Limited – IS team John Moodie/Katherine Browne/Peter Marks Taranaki IS team Brett Mahoney –Sales Rep for the contract for the software, services and support Eric Oldakowski – project manager from Wolters Kluwer (the providers of ProVation) that was assigned to the project, from the USA Midland Cancer Network project staff to support DHBs |  |  |  |  |  |  |  |  |  |
| Other stakeholders | DHB Chief Information Officers DHB Chief Operating Officers DHB Endoscopy User Groups DHB IS departments DHB capital planning forum Midland Information Systems Executive Group Taranaki IS for regional platform ProVation IS project manager |  |  |  |  |  |  |  |  |  |
| Communication Plan | Governance will be through the Midland Cancer Network Executive group. Internal DHB communication will be the responsibility of management and clinical directors of each DHB. Regional and project communications including minutes of meetings, memorandums, reports will be provided by the Midland Cancer Network. Progress reports will be provided to the Ministry of Health as requested. |  |  |  |  |  |  |  |  |  |
| Key Constraints | The project will struggle to meet the timeframes set if there are delays in IS instalment. |  |  |  |  |  |  |  |  |  |
| Project Approach and Management |  |  |  |  |  |  |  |  |  |  |
| Project approach | DHBs were asked to develop their own business cases for ProVation. Midland Cancer Network has agreed to assist as required. Healthshare Limited has provided IS support to assist with the IS component of the business case for ProVation in Bay of Plenty, Lakes and Tairawhiti. Bay of Plenty has drafted their business case which has been reviewed and final draft submitted to the Midland IS Executive group. Post sign off local DHB approval is required. Once sign off has been approved implementation of ProVation is scheduled. (Bay of Plenty is expected to commence implementation in May 2015). The same approach will be followed by Lakes then Tairawhiti. Lessons learnt from Waikato and Bay of Plenty will be reviewed when developing Lakes and Tairawhiti business cases. Commencement dates for implementation for Lakes and Tairawhiti is yet to be confirmed. |  |  |  |  |  |  |  |  |  |
| Project start date | 1 February 2015 |  |  | Project completion date |  |  |  |  | 30 June 2015 |  |
| Financial summary | Capital funding for this project is the responsibility of each individual DHB. Responsibility for the costs of the Taranaki regional platform is spread across Midland DHBs (except Waikato) Midland Cancer Network will provide project support and facilitation to DHBs as required. Healthshare Limited IS has agreed to provide IS support to the DHBs although local IS requirements will be the responsibility of local IS teams. |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  |  |  |  |  |  | Date |
| - First regional clinical meeting held to agree a consistent regional approach to the implementation of ProVation and to identify DHB requiring support with business cases. |  |  |  |  |  |  |  |  |  | March 2015 |
| 2. Second regional clinical meeting held to review progress and to ensure that both Lakes DHB and Tairawhiti DHB have drafted business cases before the Midland Executive IS board. Identify issues, risks and opportunities from the lessons learnt from Waikato and Bay of Plenty DHBs. |  |  |  |  |  |  |  |  |  | April 2015 |
| 3. Third regional clinical meeting held to review progress on implementation. a) Review issues, risks and opportunities. b) Confirm regional processes in place for implementation of ProVation c) Confirm process for managing upgrades and maintenance of ProVation across the region. |  |  |  |  |  |  |  |  |  | May 2015 |
| 4. Post Implementation review. |  |  |  |  |  |  |  |  |  | June 2015 |
| 5. Final report to the Ministry. |  |  |  |  |  |  |  |  |  | July 2015 |
| RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |
| Risks |  |  | Probability (low, med, high) |  | Impact (low, med, high) |  | Risk management strategy |  |  |  |
| Time delays in developing ProVation business case |  |  | med |  | high |  | Work with Bay of Plenty DHB staff to ensure business case completed by mid-February at the latest. |  |  |  |
| Taranaki DHB platform upgrade delayed and/or progressing through an approved process. |  |  | high |  | high |  | - Regular updates from Taranaki IS on progress made on upgrade. Escalate any issues to be resolved quickly. |  |  |  |
| Prioritisation of installation work by IS affects this projects ability to complete the milestones on time. |  |  | high |  | high |  | - Engage with project manager for IS and offer support and assistance where possible. |  |  |  |
| AUTHORISATION |  |  |  |  |  |  |  |  |  |  |
| Project Sponsor |  |  |  |  |  | Date |  |  |  |  |

| Work plan | Date |
| --- | --- |
| - Regional stocktake of where DHBs are at with their business cases. - Identify which DHBs require support with drafting of their business case. | March 2015 |
| Milestone 1 completed. | March 2015 |
| - Support the business cases at Regional IS sign-off and local DHB sign-off stages. - Support business units at Bay of Plenty, Lakes and Tairawhiti to fast track the commencement of implementation of ProVation as required. | April 2015 |
| Milestone 2 completed. | April 2015 |
| - Discuss process for managing and maintenance of future upgrades to ProVation across the region. | May 2015 |
| - Review progress on Bay of Plenty Implementation. - Review progress on Lakes and Tairawhiti Implementation. - Discuss issues, constraints and opportunities that have arisen from the implementation of ProVation and look at options for solutions. | May 2015 |
| Milestone 3 completed. | May 2015 |
| - Complete post implementation review. - Confirm status of Bay of Plenty, Lakes and Tairawhiti implementation of ProVation. - Confirm regional process to manage upgrading and maintenance of ProVation across the region. | June 2015 |
| Milestone 4 completed. | June 2015 |
| Final draft report submitted to the Ministry. | 3 July 2015 |
| Final report submitted to the Ministry. | 17 July 2015 |
| Milestone 5 completed. | July 2015 |