| Project Details |  |
| --- | --- |
| Project Title | Midland Colonoscopy Service Improvement Project 2015 |
| Sub Project 4 | Improved Referral Pathways for Direct Referral Criteria to Outpatient Colonoscopy |
| Project Sponsor | Dr Humphrey Pullon, Clinical Director, Midland Cancer Network |
| Programme Manager | Jan Smith, Manager Midlands Cancer Network |
| Project Manager | Alison Hearn, Project and Service Improvement Manager, Midland Cancer Network. |
| Clinical Lead |  |

| Document Control |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan compiled by |  | Alison Hearn |  |  |  |  |  |  |  |  |  |  |
| Associated documents |  | National Referral Criteria for Direct Access Outpatient Colonoscopy 2012 |  |  |  |  |  |  |  |  |  |  |
| Inter-related projects |  | Local DHB endoscopy service improvement Map of Medicine/Bay Navigator |  |  |  |  |  |  |  |  |  |  |
| Definitions |  |  |  |  |  |  |  |  |  |  |  |  |
| Background to project |  | In 2012, following sector feedback, the Ministry of Health published the national referral criteria for direct access outpatient colonoscopy. This was rolled out nationally with the expectation for DHBs to use and follow. Bay Navigator was developed in 2012 and is currently used to refer patients. Currently there are inconsistencies in the way in which the direct access referral criteria and triaging processes are managed across the region. The project scope will assist DHBs to adopt a consistent approach and improve the referral pathway to meet referral timeframes. |  |  |  |  |  |  |  |  |  |  |
| Project Goals |  | Operational systems and processes are in place to implement national referral criteria direct access to outpatient colonoscopy |  |  |  |  |  |  |  |  |  |  |
| Project Objectives |  | - national referral criteria for direct access outpatient colonoscopy on Map of Medicine for Waikato, Lakes and TDH DHBs - KPIs reporting system developed to monitor the number of direct access referrals per DHB - web based repository for all national, regional and local documents completed (excludes ERS) - methodology for a training programme for Primary Care Clinicians in the direct referral system developed |  |  |  |  |  |  |  |  |  |  |
| Deliverables |  | Improved utilisation of national referral criteria for direct access outpatient colonoscopy aiming up to 90%. |  |  |  |  |  |  |  |  |  |  |
| Benefits of project |  | Increased direct access to diagnostic colonoscopy services Regional enhancement of primary-secondary interface. An up to date regional MOM Reduced FSA’s |  |  |  |  |  |  |  |  |  |  |
| Coverage (inclusion) |  | Bay of Plenty, Lakes, Tairawhiti and Waikato DHBs proving publicly funded colonoscopy services. |  |  |  |  |  |  |  |  |  |  |
| Coverage (exclusions) |  | Midland region patients treated privately. Excludes publicly funded patients treated at private hospitals. Taranaki DHB Bay Navigator (as already implemented) |  |  |  |  |  |  |  |  |  |  |
| Stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |
| Expert Work Group |  | Bay of Plenty DHB Dr Abid Saadeddin – Clinical Director Mesha Premlall - Clinical Nurse Manager Lakes DHB Dr Charlie Richardson – Clinical Director Chrissy Rees – ACNM – Perioperative Area Tairawhiti DHB Dr Peter Stiven Dawn Tucker - Theatre Manager Waikato DHB Dr Graeme Dickson – Clinical Director Andrea Coxhead – Business Unit Manager, Medicine and Endoscopy Helen Goldsmith – Charge Nurse Manager |  |  |  |  |  |  |  |  |  |  |
| Other stakeholders |  | Damian Tomic, Clinical Director Primary Care, MOM team. Primary Care Clinicians and Managers across the Midland region. Referral Centre staff in each Midland DHB. |  |  |  |  |  |  |  |  |  |  |
| Communication Plan |  | Governance of the project will be through the Midland Cancer Network Executive group Internal DHB communication as and when required will be the responsibility of management and clinical directors of each DHB |  |  |  |  |  |  |  |  |  |  |
| Key Constraints |  | Short time frame to complete project work |  |  |  |  |  |  |  |  |  |  |
| Project Approach and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Project approach | The project team will undertake to work with individual DHBs. Following a stocktake of each DHB referral pathway we will: - Work on the Map of Medicine and align the work done on the Bay Navigator. A meeting is to be held on the 10th March with MOM personnel to discuss the possibilities of uploading the national criteria. - Work with data analysts to develop a reporting tool for monitoring direct referrals. A KPI dashboard is considered as a reporting tool for direct referrals. - Develop a regional web-based page for colonoscopy information that is not held in any other place (i.e. MOH, MOM and Bay Navigator) - Discuss with each DHB how they could implement training of the GPs in better use of the national criteria |  |  |  |  |  |  |  |  |  |  |  |
| Project start date | 1 February 2015 |  |  |  |  | Project completion date |  |  |  | 30 June 2015 |  |  |
| Financial summary | Midland Cancer Network will provide project support and facilitation to DHBs as required and the MOM team |  |  |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  |  |  |  |  |  |  | Date |  |
| 1. - Completed stocktake. Review the consistency of implementation of the national criteria and consider options for improvement of the referral pathway - Process for developing a pathway for the national criteria on Map of Medicine commenced- - Develop the web based repository page to capture national, regional and local colonoscopy documents such as service plans; capacity plans and data sets. - Determine KPIs to be used for reporting and monitoring |  |  |  |  |  |  |  |  |  |  | March 2015 |  |
| - KPI’s and web repository content agreed |  |  |  |  |  |  |  |  |  |  | April 2015 |  |
| - Map of Medicine updated with National Referral Criteria for Direct Access Outpatient Colonoscopy for each DHB |  |  |  |  |  |  |  |  |  |  | May 2015 |  |
| - a) KPI reporting started b) Web-based repository page completed and documents uploaded. |  |  |  |  |  |  |  |  |  |  | June 2015 June 2015 |  |
| - Planning for regional training sessions on the use of the National Referral Criteria for Direct Access Outpatient Colonoscopy completed. |  |  |  |  |  |  |  |  |  |  | June 2015 |  |
| - Feedback on impact of standardised referral pathways completed. |  |  |  |  |  |  |  |  |  |  | June 2015 |  |
| - Final report to the Ministry. |  |  |  |  |  |  |  |  |  |  | July 2015 |  |
| RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| Risks |  |  | Probability (low, med, high) |  | Impact (low, med, high ) |  | Risk management strategy |  |  |  |  |  |
| Delay in uploading criteria onto the Map of Medicine and aligning to Bay Navigator |  |  | med |  | med |  | Work with the MOM unit and directors to complete the work |  |  |  |  |  |
| AUTHORISATION |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Sponsor |  |  |  |  |  |  |  | Date |  |  |  |  |
| Work plan |  |  |  |  |  |  |  |  |  |  |  | Date Due 2015 |
| Meet with data analyst to scope data requirements for KPI (direct access) Contact and visit individual personnel to introduce the project to ascertain current practice and utilisation of the criteria |  |  |  |  |  |  |  |  |  |  |  | 10 March 8 March |
| Determine the process to upload the National Referral Criteria for Direct Access Outpatient Colonoscopy onto Map of Medicine Develop web-based repository layout and content agreed. Determine KPIs with the group for reporting/monitoring purposes |  |  |  |  |  |  |  |  |  |  |  | 12 March |
| Milestone 1 completed. |  |  |  |  |  |  |  |  |  |  |  |  |
| Agree the proposed KPIs and web based repository page. |  |  |  |  |  |  |  |  |  |  |  | 23 April |
| Milestone 2 completed. |  |  |  |  |  |  |  |  |  |  |  |  |
| Update Map of Medicine with standardised referral criteria. |  |  |  |  |  |  |  |  |  |  |  | 30 May |
| Milestone 3 completed |  |  |  |  |  |  |  |  |  |  |  |  |
| Review progress with the uploading of national criteria to the Map of Medicine |  |  |  |  |  |  |  |  |  |  |  | 28 May |
| Review the progress of KPIs |  |  |  |  |  |  |  |  |  |  |  | 28 May |
| Milestone 4 completed |  |  |  |  |  |  |  |  |  |  |  |  |
| Discussion with each DHB as to how to incorporate GP training on the utilisation of the national criteria |  |  |  |  |  |  |  |  |  |  |  | May to June |
| Milestone 5 completed. |  |  |  |  |  |  |  |  |  |  |  |  |
| Web-based repository completed and information uploaded |  |  |  |  |  |  |  |  |  |  |  | 30 June |
| Collate feedback on impact of standardised (MOM)referral pathways |  |  |  |  |  |  |  |  |  |  |  | 30 June |
| Milestone 6 completed |  |  |  |  |  |  |  |  |  |  |  |  |
| Final draft report |  |  |  |  |  |  |  |  |  |  |  | 3 July |
| Final report submitted to the Ministry |  |  |  |  |  |  |  |  |  |  |  | 17 July |
| Milestone 7completed. |  |  |  |  |  |  |  |  |  |  |  |  |