| Project Details |  |
| --- | --- |
| Project Title | Midland Colonoscopy Service Improvement Project 2015 |
| Sub-project 3 | Regional waitlist management initiative |
| Project Sponsor | Dr Humphrey Pullon, Clinical Director, Midland Cancer Network |
| Programme Lead | Jan Smith, Manager Midland Cancer Network |
| Project Manager | Lu-ana Ngatai, Service Improvement and Project Manager |
| Clinical Lead | TBC |

| Document Control |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan compiled by | Lu-ana Ngatai |  |  |  |  |  |  |  |  |  |
| Associated documents | Elective Services Health Target Diagnostic Colonoscopy performance indicators |  |  |  |  |  |  |  |  |  |
| Inter-related projects | DHB Elective Services Action Plans Midland Faster Cancer Treatment plan 2014/15 |  |  |  |  |  |  |  |  |  |
| Definitions |  |  |  |  |  |  |  |  |  |  |
| Background to project | DHBs are in the process of improving wait list management. There is known variance in waitlist management across the region. The growth of surveillance patients across the region is of concern to both clinicians and management as it is becoming more difficult to clear the waitlist for these patients. Experience from overseas has shown that low waits for colonoscopy are achievable with robust waitlist management processes, alongside careful detailed regular planning of capacity and in depth understanding of the productivity (NEQIP 2015). |  |  |  |  |  |  |  |  |  |
| Project Goal | Improved standardised wait list management in each DHB. Tools are in place to continue to improve local waitlist systems and processes. |  |  |  |  |  |  |  |  |  |
| Project Objectives | To review current referral to triage, waitlist and booking system practices across the region. Identify areas of variation. To identify areas of improvements for managing referrals, waitlists and booking systems. Implement prioritised improvements. To utilise other regions local waitlist and booking system management models to improve patient wait times. |  |  |  |  |  |  |  |  |  |
| Deliverables | Regional consistent approach to managing colonoscopy waiting lists. |  |  |  |  |  |  |  |  |  |
| Benefits of project | Improved and consistent waiting list management to ensure accurate tracking, triaging and management of patients waiting. |  |  |  |  |  |  |  |  |  |
| Coverage (inclusion) | Publicly funded Bay of Plenty, Lakes, Waikato and Tairawhiti DHB patient waitlists for colonoscopy services. |  |  |  |  |  |  |  |  |  |
| Coverage (exclusions) | Taranaki DHB. Patients treated in private. |  |  |  |  |  |  |  |  |  |
| Stakeholders |  |  |  |  |  |  |  |  |  |  |
| Expert Work Group | Bay of Plenty DHB Dr Abid Saadeddin – Clinical Director Neil McKelvie – Service Manager Mesha Premlall - Clinical Nurse Manager Lakes DHB Dr Charlie Richardson – Clinical Director Greg Vandergoot– Service Manager Ann-Maree Murphy – Colorectal Nurse Specialist Chrissy Rees - ACNM – Perioperative area Tairawhiti DHB Dr Peter Stiven – Clinical Director Lynsey Bartlett – Acting Chief Operating Officer Dawn Tucker – Theatre Manager Waikato DHB Dr Graeme Dickson – Clinical Director Amanda Wright – Service Manager Andrea Coxhead – Business Unit Leader Helen Goldsmith – Charge Nurse Manager Amanda DeSouza – Registered Nurse Endoscopy Decision Support staff from each of the Midland DHBs Midland Cancer Network project staff |  |  |  |  |  |  |  |  |  |
| Other stakeholders | Midland DHB Chief Operating Officers Midland DHB GMs Planning and Funding NEQIP team Booking Clerks at each DHB Ministry of Health DHB Electives Team |  |  |  |  |  |  |  |  |  |
| Communication Plan | Internal DHB communication as and when required will be the responsibility of management and clinical directors of each DHB. Regional and project communications including minutes of meetings, memorandums, reports will be provided by the Midland Cancer Network. |  |  |  |  |  |  |  |  |  |
| Key Constraints | Ability to access regional data. |  |  |  |  |  |  |  |  |  |
| Project Approach and Management |  |  |  |  |  |  |  |  |  |  |
| Project approach | The MCN project resource will support and work in collaboration with DHBs to: - stocktake the current situation - identify variation and - support improvements We will also review what management tools are used elsewhere, and utilise this information to assist the DHBs. |  |  |  |  |  |  |  |  |  |
| Project start date | 1 February 2015 |  |  | Project completion date |  |  |  |  | 30 June 2015 |  |
| Financial summary | Midland Cancer Network will provide project support and facilitation (as required) to DHBs who will be leading the work. |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  |  |  |  |  |  | Date |
| - Stocktake of local referral, wait list and booking processes. |  |  |  |  |  |  |  |  |  | 23 April 2015 |
| - Undertake analysis of wait list patient flows across the region. |  |  |  |  |  |  |  |  |  | 28 May 2015 |
| - Review unit level management tools used in other DHBs. - Consider options for improving waitlist management across the region. |  |  |  |  |  |  |  |  |  | 28 May 2015 |
| - Draft and final report to Ministry. |  |  |  |  |  |  |  |  |  | July 2015 |
| RISKS AND RISK MANAGEMENT |  |  |  |  |  |  |  |  |  |  |
| Risks |  |  | Probability (low, med, high) |  | Impact (low, med, high) |  | Risk management strategy |  |  |  |
| Staff resistance to change in waitlist methodology. Everyone wants their own version. |  |  | med |  | high |  | Clinical leads and managers to work with staff on service improvements. |  |  |  |
| AUTHORISATION |  |  |  |  |  |  |  |  |  |  |
| Project Sponsor |  |  |  |  |  | Date |  |  |  |  |

| Work plan |  |
| --- | --- |
| Commence gathering of local data from each DHB. | 12 March 2015 |
| Meetings held with CNS and booking clerks at each DHB to understand and confirm referral, triaging, waitlist and booking systems and processes. | 17 April 2015 |
| Prepare a stocktake of local patient management practices. | 17 April 2015 |
| Review available NEQIP documentation on referrals, triaging, wait list and booking systems. | 17 April 2015 |
| Review stocktake of current waitlists in the region and data reporting. | 20 April 2015 |
| Present stocktake to working group for further discussion. | 23 April 2015 |
| Determine local and regionally consistent waitlist issues and provide options for working group to consider | 23 April 2015 |
| Milestone 1& 2 completed. | 23 April 2015 |
| Review and present unit level waitlist and demand and capacity models being used across the country to working group | 28 May 2015 |
| Consider any standardised improvement options that could be implemented locally in DHBs. | 28 May 2015 |
| Agree improvements and work with local DHBs as required to make changes. | 28 May 2015 |
| Milestone 3 & 4 completed. | 28 May 2015 |
| Draft report submitted to the Ministry. | 3 July 2015 |
| Final draft report submitted to the Ministry. | 17 July 2015 |
| Milestone 5 completed. | 17 July 2015 |